## Summary
MS Projects
is a super useful tool for scheduling huge activities
The tool offers many functionalities to consider create , plan the schedule
It works similarly to excel but just that it is used for scheduling work
This is a super useful tool for scheduling big projects with many activities.
The tool offers many functionalities to help you create, change and control your project schedule most efficiently.

## Line insert
How to insert a task or a line
| Go to the particular line or row & then click right click button in mouse & a popup notification is displayed | ok
Next click Insert task button as highlighted in above screen shot

## Entering dates
How to enter the date in MS Projects file
First enter the number of days in Duration column & then enter the start date
Automatically MS Projects file will capture the Finish date

## Basic screen
ok
To the left we have the main table where the tasks need to be listed and scheduled.
(Highlighted in pink)
To the right, we have the Gantt Chart field which is automatically populated as you type in your tasks.
(Highlighted in dark green)
Above, we also have a timeline indicator to which you can add manually selected tasks.
This can be hidden

## Expanding the main part
ok
The main part can be expanded by swiping the gantt chart to the right. Use the cursor or arrow mark displayed in screen as highlighted in screen shot.

## Basic Column information
Let's start with the task name. You need to type the name in the field.
Then we have duration where you can select the duration in days, weeks or months.
After you have start & finish dates
This is where you need to select the calendar day on which the tasks will start and finish.
Moving further to the right you have predecessors.
This is the field where you indicate dependencies between the tasks.
Then - resource names columns. Here you tell the name or role of the person responsible for the task at hand.
The last one is add new column and from the dropdown you can see many other options you can add. We won't view them but to give you an example - % complete - by clicking on it it creates a new column.

## Example
Below example is a project plan for refurbishing the room
You would have the following tasks: remove old furniture Before starting anything you need to empty the
room
You deem 2 days are an appropriate duration and fill it in.
Then you need to say which date it should start. Spring sounds good.
Let's say April 8th. By typing it the tool automatically calculates the end date(Date mentioned in Finished column).
Resources -
let's say your brother is the person to do the heavy lifting.
Next cover the floor.
So nothing gets dirty during painting.
Let's say one day. Now this one should start after we have removed the furniture, right? So we have a dependency.
We need to use the predecessors field and we have two ways to do this.
Select the two tasks and click on link tasks.
Select the two tasks and click on link tasks.
There you go.
It automatically populates the start date on the day after the first task is finished.
Resource - let's say your father will be doing the covering and painting.
Next -
Paint the room. Let's say - five days.
Again this is dependent on the floor covering.
We will do the same but this time we will show you the other way.
You can directly type into the predecessor field the number of the task on which this one is dependent.
So 2. After painting we will position the new furniture.
Let's say - 2 days.
We will again use the dependency typing 3.
We will again use the dependency typing 3.
Finally - some decoration - using the same logic and assigning your sister.
There you go.
You have a plan.

## Sheet1
Create Notes from Udemy modeule about project management
for example about indent task
How to add 5 new rows

## Summary task
Summary task
Is a very important functionality
For example ,We want to see the painting activities in more detail under the activty " Paint the room"
Select a few rows beneath a particular task
Here after the row Paint the room the user has selected a few rows , lets say 5 rows as illustrated in the below screen shot
Now click Insert task
As you see in the below screen shot , 5 new rows are created
we want to plan when to paint the walls and the ceiling. Hence the user has typed Wall1, wall2 …...
We type them in the same way.
However they are now displayed as new independent tasks.
We need to indicate they are part of the paint room parent activity so we select them and use the indent
task button.
Now, they are all subtasks to the main one "Paint the room".
There is a dashline"-" prior to Paint the room. This symbol indicates that there are subtasks.
Now just like any other tasks fill up the dates, durations for all the five subtasks
You can also double click on each task to open up a window.
Here you can see many details including all of the functionalities we saw.
For example, predecessor tab gives you information on all dependencies.
Also notes where you can type
additional information on a task.
After completing the plan to the right you can see the Gantt Chart
that MS project has automatically created for you.
An illustation is provided where you can see to the right the activity list with durations, start and end dates and dependency indicator in the predecessor column.
Note: this is the high level summarized version.
However, we have 144 lines.
Here in the below screen shot you can identify as to how there are 144 lines in the project plan
This means we have the full list including many subtasks. All activities with a plus sign to their right
and in bold
are summary tasks. Just click on the plus to expand.
Let's see a few of them. Expand
"Prepare land for construction".
It has three subtasks: assemble and position safety barriers,
Clear site, etc..
Car manufacturing: schedules for 6 cars - by expanding them
you can see all the production steps identified. Recruit personnel -
Same thing. As explained at the beginning MS project is easy to use and quite useful when planning projects.

## Notes
Udemy course
Basics:
Resources: The profile that is needed to perform a particular task. For Testing we will need Test analysts, Testers, Test Leads, Subject Matter Experts etc So these are all regarded as resources.
Allocation: is defining the resources for a particular task
Scheduling : is the estimation of duration for a particular task. Estimating comes along with experience. The more the experience the better the estimation.
Predecssor: in general means the task preceding. In simple terms you can say the task that is coming before a particluar task.
Sucessor: means the task that is next to the present one.
Gantt chart : is a series of horizontal lines that shows the amount of work done. In a nut shell it is a chart or a graph representing overall progress along with specific dependencies.
Critical Task: is the longest duration in milestones.

## Menu Bar
Menu Bar:
The tabs consisting of File , Task, Resource, Report, Project etc are all menu bars in a MS Project tool.
Screen shot of the same is provided below:
In File there are multiple options & these are represented as Nes, Open, Save, Saveas , Print etc.
Refer the below screen shot for more details.