## GANTT
[10 empty] | Jan'21 |  |  |  | Feb'21 |  |  |  | Mar'21 |  |  |  |  | Apr'21 |  |  |  | May'21 |  |  |  | Jun'21 |  |  |  |  | Jul'21 |  |  |  | Aug'21 |  |  |  |  | Sep'21 |  |  |  | Oct'21 |  |  |  | Nov'21 |  |  |  |  | Dec'21
Program level activities | time axis 2021-01-04 to 2021-12-13
Due Diligence | [9 empty] | 2021-01-11: 1; 2021-01-18: 2; 2021-01-25: 3; 2021-02-01: 4; 2021-02-08: 5
Report Out and Business Go Ahead | bar: 2021-02-15; 2021-03-08
SOW Execution | [9 empty] | 2021-03-15: 1; 2021-03-22: 2; 2021-03-29: 3; 2021-04-05: 4
Technology Implementation Infra / Technology set up @ EXL | [19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Prudential Id Creation | [27 empty] | 1 | 2 | 3 | 4
[10 empty] | Jan'21 |  |  |  | Feb'21 |  |  |  | Mar'21 |  | 4: Apr'21; 8: May'21 |  |  |  | Jun'21 |  |  |  |  | Jul'21 |  |  |  | Aug'21 |  |  |  |  | Sep'21 |  |  |  | Oct'21 |  |  |  | Nov'21 |  |  |  |  | Dec'21
Sr. No | Function / Processes | Complexity | Knowledge Transfer Model | FTE | HC | Location | Process Traning | Nesting | Ramp up (weeks) | time axis 2021-01-04 to 2021-12-13
| Annuities Bene Services |  | Remote |  |  | Noida |  |  |  | 2021-10-25: Calibration & Certification
1 | Follow up Letters and RSA Validation | L3 |  | 5 | 7 |  | 3 Weeks | 2 Weeks | 14 Weeks | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | Hands on practice to continue to retain the knowledge
2 | APO Payments and Lump Sum Payments | L3 |  | 5 | 8 |  | 4 Weeks | 2 Weeks | [28 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Hiring |  | *plus 2 for quality audits
Pre-Process
Process Training
Nesting
Ramp/Pilot
Go Live
Steady State
Checkpoint Tollgate