## Slide 1
CASE STUDY: RKS – analysis
Claim notifications are received via Website, EDI feed, or Contact Center, or death notification mailbox. Condolence package to be sent for claims
FTE migrated
03
Processes
Transition Timelines
GUL
110 days (From training to ramp)
FTE’s
Knowledge Transfer
Back Office – 03 FTE
4 week of remote training via MS Teams in WFH environment to provide basic overview of the process and system training
Weekly PKT conducted for knowledge check
Team started hands on practice from Jun 14 and managed to practice 614 files during nesting phase
Mapping of EXL resources with one client SME for better query and feedback mechanism
Relevant SOPs/Job-aids are made available within Pru environment
Complexity / Languages
Operations Management
Level 3 BO (Project Management) / English
6 out of 7 resources externally hired and 1 seeded internally
Regular connect with client– Daily/Weekly, for performance review
Quality SLA’s proposed by Client were jointly agreed. EXL team over achieve from day 1 of ramp phase
One dedicated client SME was aligned with EXL team for on time feedback
Team able to churn 100% volume within 1 day TAT
Sending locations
Transformation
Dresher; Roseland (United States)
No transformation involved in the process migration
Receiving locations
India – Noida
Dedicated project manager to ensure governance and oversight
Tollgate review & approval from internal and external stakeholders prior moving to next phase of Transition
Program Management
Project Scope
Solution Highlights
Outcomes
Days, total transition time
110
Highlights:
Team able to
Team performance has been appreciated by Client key stakeholders