## Title Page
'Handover to Operations' Criteria - Status Report
The 'Handover to Operations' will be seeking to confirm that a number of pre-defined 'entry' criteria, provided by all Workstreams (Business, Programme and InfoSec contributors) have been met or are on track to be met. The criterion are a sub-set of Programme, Business and InfoSec readiness activity plans and are aimed at providing the evidence to support a decision. The decision to formal handover will only be made if all approvers vote unanimously.
Prior to the handover there could also be a series of weekly sessions to discuss the relevant criteria and assign a status (Blue, Red, Amber or Green). At the final meeting, criterion which are outstanding (i.e. not completed) will be tabled and an action plan agreed. The process will be repeated for each migration separately.
Where individual criteria are listed as a 'Red' status, they will be recorded and managed through the Project Risks & Issues Log. Also, incase there are any assumptions made to a criteria based on the evidence or agreement between the stakeholders, these assumptions will be recorded in the project assumption log.
Date: 23-Aug-21
Author: Sayantan Ghosh
Process: Prudential Group lIfe Claims (GL Mailbox+ Paper Mail; GUL & RKS)
Version:
Owner: Sayantan Ghosh
Sign Off
Checklist

## Hand Over to Operations
Handover Document: Migration to Operations Version 1.1
Description |  |  | Score | Status
Task or activity delayed, re-plan required, impacts other tasks |  |  | 0 | Red
Task or activity delayed, recovery plan in place, due date still achievable |  |  | 1 | Amber
Task or activity on track or complete, awaiting evidence of completion |  |  | 2 | Green
Task or activity complete and evidence of completion received |  |  | 3 | Blue
Task or activity not applicable to current migration, or not yet due to be started |  |  | NA | Grey
2.9
S. No. | Category | Sub-heads | Owner | Status | Remarks | Target Date
1 | Agreements/ Legal | Is SOW signed-off? | Sayantan | 2 | First draft shared with Jagan & kamesh for review
|  | Has approval been received from Legal? | Sayantan | 2 | WIP
2 | Plans and Analysis | Project plan/ key project timelines shared? | Sayantan | 3 | Shared with Ops
|  | If applicable, has a volume and/or FTE ramp-up plan been handed over? | Sayantan | 3 | Was part of weekly Pack
|  | Was Risk and Mitigation Log shared? | Sayantan | 3 | Was part of weekly Pack
|  | Was baselined volumes, trends, time and motion sheets etc. shared? |  | 3
|  | Are Pilot and Steady state SLA metrics signed off? | Sayantan | 3 | Part of SOW
3 | Documentation | Are business signed-off process maps and SOPs in place? | Sayantan | 3 | Available in Prudential Network
4 | Quality Process | Has the Quality audit sheet been signed off? Has the timeline to start QC monitoring been documented? | Gulshan | 3 | Available within Pru environment
|  | Have QCA's for all processes identified? | Sayantan | 3 | Yes, RKS QA training completed. Certification is in progress
5 | Tollgates | Were all Tollgates for the project signed-off by key stakeholders? | Sayantan | 3 | All Tollgates signed off by Client & Exl Stakeholders
|  | Are there any open items from Commencement tollgate? Has a plan been put around their closure? | Sayantan | 3 | No Open items
6 | Staffing | Have all Customized JD and skill set documents been handed over? | Sayantan | 3 | Available in Prudential shared path
7 | Technology | Have accesses been received for all in-scope client applications? | Sayantan | 3 | All resources have access to in scope apps
|  | Has business application ID process been documented? | Sayantan | 3 | Part of OSD
|  | Has B-ProMPT/PTS been set up and being updated? | Sayantan | 3 | B Prompt is been used currently, however, PTS is not used by EXL Ops
8 | Training | Have pre-process attendance and scores been handed over? | Sayantan | 3 | All scores are recorded and have been made available for Ops managers
|  | Have process training attendance, assessments and scores been handed over? | Sayantan | 3 | Recorded in training update report
9 | Reports | Are all reporting requirements signed off by business? Is the MI distribution list agreed? | Sayantan | 3
|  | Have all reporting templates been signed off by business and handed over? Have at least the first set of agreed reports been circulated? | Sayantan | 3 | Existing Reporting approach to be followed
10 | Others | Has the OSD frame work been established and handed over / signed off by AVP/VP Operations? |  | NA
|  | Has the BCP plan been documented and signed -off? |  | NA | N/A
|  | Where applicable, have AM and trainer (any one else from transition team) travel bonds been completed and handed over to line HR? |  | NA | N/A
Sign Off
Home

## Sign Off
Approvals
The following stakeholders here by approve to commence provision of the services by EXL subject to any outstanding actions detailed in this document.
Stakeholders |  | Title | Approval
Kamesh Sharma |  | Sr. AVP (Ops)
Shikha Saini |  | Sr. Manager (Ops)
Jagan Mohan |  | Sr. AVP (Transition)
The role of the owner (own the criterion - Client or EXL) is to provide an update/ recommendation to the stakeholders for their specific areas of ownership and responsibility.
Owners |  | Title | Approval
Client
EXL
YES
NO
Home