## Slide 1: prudential Group claims notification Paper mail Ramp up
Jun 11 2021

## Slide 2
Transition summary
Access Creation
BAU
Process Training
Nesting
Transition Status
Transition SOW:
SOW has been fully executed on May 17
Transition for Paper mail commenced from Apr 26
Resources:
Total 6 resources deployed against the requirement of 4 FTEs
These 4 FTEs will be utilized to manage both GL Mailbox & Paper mail
Knowledge Transfer (KT):
Process training completed by May 14
Day on day training schedule and SOPs are available within Pru environment
System Accesses:
All resources have an access to all in-scope applications and WFH set up is enabled
Ramp Up Readiness:
Ramp Audit Plan:
Pru to pick up audit for EXL during ramp phase. Quality sampling size agreed with Pru. Pru SMEs will pick up 50% sample for first 5 weeks and 25% from week 6 and during steady state
EXL QA has been identified and shared with Pru. Training & certification process is in progress
SLA - Quality Target for EXL resources to be discussed and agreed with Pru for ramp and steady state
Volume: Week on Week ramp volume agreed with Pru, however, the actual inflow will depend on the file availability
Release status:
As per effort estimation, total 4 FTEs are needed to handle Paper mail & GL Mailbox, however, EXL deployed 6 resources in total
All 6 resources will start ramp from w/c Jun 14
Timelines
March - 21 | April - 21 | May - 21 | June – 21 | July - 21
15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
4 FTEs
Ramp up
Paper Mail
GL Mailbox
Moved to Steady State from WC 06/07

## Slide 3
Paper mail - Performance dashboard
Key Points/Observations
Nesting Performance Snippet:
Paper Mail:
Total number of cases processed during nesting phase - 391
Quality audits performed for 100% cases
Over all 2 feedback received on May 17
Feedbacks shared with team in an expedited manner to avoid repetition in errors
Team achieved 100% quality score since day 2 of Ramp
Queues in scope: Non restricted files
Queues out of scope: Restricted Files
Quality (Critical) :
Paper mail: 50% transactions first 5 weeks & then 25% transaction from week 6 and during steady state
  Quality audits will be performed by Pru SMEs till steady state
  Well defined quality audit parameters are available in Quality Tracking System (QTS) to record audit score.
  Quality target and quality ramp plan to be discussed and agreed
Volume/Production:
Week on week ramp volume agreed with Pru, however, the actual volume is on the lower side due to seasonality
TAT (Turn Around Time)
100% of agreed ramp volume to be touched on the day of receive
*Performance data is from 02/08/2021 to 04/02/2021

## Slide 4
Go/ No - go Tollgate
Parameters | Status | Comments
Legal & Contract |  | Change Request executed on May 17. No Specific requirement identified during KT to initiate any further change
Organization & People |  | 06 resources deployed for GL Mailbox & Paper Mail. Total 6 resources deployed against the requirement of 4 FTEs
Quality (Audits during Ramp and Steady State) |  | EXL QA names shared with Pru. Training & certification process is in progress. Pru to do quality checks during ramp phase
Training |  | Training took place via MS Teams as per plan. SOPs/Job aids available in Prudential share point.
Process SOP/Workflow Design |  | No SOP updation requirement identified. SOPs are available in SharePoint. Existing workflow design to be followed and is available in prudential network.
Communication/Governance Plan |  | Weekly operation touch base meetings scheduled between Prudential and EXL stakeholders
SLA Baselining & Data Collection |  | EXL to start the SLA baselining activity once the team moved to steady state
Infrastructure & Technology |  | Applications access granted for all users. No hardware & software requirement is pending. WFH enabled for all users
Status | Description
 | Task or Activity delayed, re-plan required, impacts GNG or other tasks
 | Task or Activity delayed, recovery plan in place, due date still achievable
 | Task or Activity on track or complete, awaiting evidence for sign off
 | Task or Activity complete
 | Task or Activity planned, but not due to be started

## Slide 5
Action items
Process | Action items | Next Steps | Responsibility | Target Completion Date | Status
Paper Mail | Daily volume to be monitored for effort estimation | Daily inflow from Jun 14 to be monitored for 1st and 2nd week of ramp for better FTE utilization | Ranjan / Sayantan | Jun 25 | Yet to Start
 | EXL QA identification to be done | EXL QA training certification is in progress. Certification process will be completed by Jun 25 | Patti | Jun 25 | WIP
 | Daily Ramp MIS to be published | Daily weekly MIS to be published with Pru and all the stakeholders to monitor the ramp performance Standard MIS format to be used to track the performance (Productivity & Quality) | Sayantan | Ongoing | Yet to Start

## Slide 6: annexure

## Slide 7
Governance during Ramp-up
Forum | Frequency (Suggested Timeline) | Activities | Participants | 
 |  |  | Prudential | EXL
Daily Ramp MIS | Daily (Email); Weekly performance pack | EXL to share daily performance MIS with Pru from May 17 onwards. Also a weekly summary to be produced for senior leadership team and weekly review call | Vendor Management: Mark Smith Operations: Maria Lopes Joseph Bianco Patricia Waskiewicz | Operations: Kamesh Sharma Shikha Saini Ranjan Banerjee Transition: Jagan Mohan Sayantan Ghosh
Weekly Transition Review | Weekly | Review of weekly ramp performance | Vendor Management: Mark Smith Operations: Maria Lopes Joseph Bianco Patricia Waskiewicz | Operations: Kamesh Sharma Shikha Saini Ranjan Banerjee Transition: Jagan Mohan Sayantan Ghosh
Frequency of meetings & attendee list is subject to change as per Business requirement

## Slide 8
Proposed exl operating structure
Operations
Transitions
Kamesh Sharma
Senior AVP - Operations
VP 2 - Operations
Ajay Singh
Ranjan Banerjee
Quality Auditors
Sayantan Ghosh
Sr Manager – Transitions
Jagan Mohan
Sr. AVP – Transitions
Account Management
VP 2 – Account Management
Sarika Gupta
Shared resource
Dedicated resource
Quality & Process Excellence
Amit Srivastav
VP – QPE
Mohit Marwah
Sr Manager-QPE
Gulshan Kumar
Asst. Manager - QPE
Shikha Saini
Manager – Operations
Lead Asst. Manager - Operations
Senior AVP – QPE
Vijay Rawat
VP –Account Management
Kunal Kapoor
Ops Associates (8 FTEs)
Dhirendra Singh
VP - Operations

## Slide 9: Thankyou