## Slide 1: prudential Group claims notification Paper mail Steady State
Jul 9 2021

## Slide 2
Transition summary
Access Creation
BAU
Process Training
Nesting
Transition Status
Transition SOW:
SOW has been fully executed on May 17
Transition for Paper mail commenced from Apr 26
Resources:
Total 6 resources deployed against the requirement of 4 FTEs
These 4 FTEs will be utilized to manage both GL Mailbox & Paper mail
Knowledge Transfer (KT):
Process training completed by May 14
Day on day training schedule and SOPs are available within Pru environment
System Accesses:
All resources have an access to all in-scope applications and WFH set up is enabled
Ramp Performance:
Team started ramp from Jun 14
  Productivity: Team received 1140 files till Jul 8 and able to churn the volume within the agreed TAT
  Quality: 100% quality achieved form day 1 of ramp against the target of 98%
  Volume: Team received 1140 files against the target of 868 files till Jul 8
Steady State Readiness:
Go ahead received from Pru on Jul 7
1 EXL QA has been certified and will start picking up the QC for both GL Mail box & Paper mail
Release status:
As per effort estimation, total 4 FTEs are needed to perform GL Mailbox + Paper mail work, however, EXL deployed 6 resources in total
All 6 resources are expected to move to BAU from Jul 12
Timelines
March - 21 | April - 21 | May - 21 | June – 21 | July - 21
15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26
4 FTEs
Ramp up
Paper Mail
GL Mailbox
Moved to Steady State from WC 06/07

## Slide 3
Paper Mail- Performance dashboard
*Performance data is from 02/08/2021 to 04/02/2021
Key Points/Observations
Queues in scope: Non restricted files
Queues out of scope: Restricted Files
Quality (Critical) :
Paper Mail: Team achieved 100% accuracy from day 1 of ramp
  Quality audits performed by Pru SMEs as per the agreed %
  Well defined quality audit parameters are available in Quality Tracking System (QTS) to record audit score
  EXL QA will pick up the QC. QC sample will be pulled by EXL QA
Volume/Production:
Team received 1140 files against the target of 868 files till Jul 8
A significant improvement noticed in restricted volume. Team experienced only 31% restricted volume in last 4 weeks
TAT (Turn Around Time)
100% of agreed ramp volume to be touched on the day of receive
Individual Ramp Performance
Week | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  | 
Date | 14-Jun | 15-Jun | 16-Jun | 17-Jun | 18-Jun | 21-Jun | 22-Jun | 23-Jun | 24-Jun | 25-Jun | 28-Jun | 29-Jun | 30-Jun | 1-Jul | 2-Jul | 5-Jul | 6-Jul | 7-Jul | 8-Jul | 9-Jul
FTE | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Planned Volume | 42 | 42 | 42 | 42 | 42 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 56 | 56 | 56 | 56 | 56
Proposed Quality | 85% | 85% | 85% | 85% | 85% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 98% | 98% | 98% | 98% | 98%
Sample Size | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Volume Received | 91 | 132 | 68 | 65 | 41 | 85 | 56 | 41 | 53 | 41 | 61 | 68 | 38 | 63 | 43 |  | 88 | 58 | 48 | 
Restricted | 26 | 29 | 14 | 18 | 6 | 37 | 29 | 16 | 7 | 17 | 18 | 34 | 18 | 20 | 16 |  | 34 | 17 | 21 | 
Non-Restricted | 65 | 103 | 54 | 47 | 35 | 48 | 27 | 25 | 46 | 24 | 43 | 34 | 20 | 43 | 27 | 0 | 54 | 41 | 27 | 0
Non-Restricted % | 71% | 78% | 79% | 72% | 85% | 56% | 48% | 61% | 87% | 59% | 70% | 50% | 53% | 68% | 63% | #DIV/0! | 61% | 71% | 56% | #DIV/0!
Quality Achieved | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | w/o | 100% | 100% |  | 
Holiday

## Slide 4
Go/ No - go Tollgate
Parameters | Status | Comments
Legal & Contract |  | SOW executed on May 17. No Specific requirement identified during Ramp to initiate any further change. Steady state SOW to be executed towards the end of last transition
Organization & People |  | 06 resources deployed for GL Mailbox and Paper Mail. Total 6 resources deployed against the requirement of 4 FTEs
Quality (Audits during Steady State) |  | EXL QA has been certified and will pick up quality audit form day 1 of steady state. Quality sample will be pulled by EXL QA
Training |  | Training took place via MS Teams as per plan. SOPs/Job aids available in Prudential share point.
Process SOP/Workflow Design |  | No SOP updation requirement identified. SOPs are available in SharePoint. Existing workflow design to be followed and is available in prudential network.
Communication/Governance Plan |  | BAU governance plan has been agreed jointly with Pru
SLA Baselining & Data Collection |  | EXL to start the SLA baselining activity post 90 days once the team (including Paper Mail) moved to steady state
Infrastructure & Technology |  | Applications access granted for all users. No hardware & software requirement is pending. WFH enabled for all users
Status | Description
 | Task or Activity delayed, re-plan required, impacts GNG or other tasks
 | Task or Activity delayed, recovery plan in place, due date still achievable
 | Task or Activity on track or complete, awaiting evidence for sign off
 | Task or Activity complete
 | Task or Activity planned, but not due to be started
GO / No-Go checklist

## Slide 5
Action items
Process | Action items | Next Steps | Responsibility | Target Completion Date | Status
Paper Mail | Daily Ramp MIS to be published | Daily weekly MIS to be published with Pru and all the stakeholders to monitor the ramp performance Standard MIS format to be used to track the performance (Productivity & Quality) | Sayantan | Jul 9 | WIP
 | Performance monitoring: Performance of all 6 resources to be monitored during steady state | Performance to be monitored continuously and to be included in the work stream meeting pack | Ranjan | Ongoing | WIP
 | SLA Baselining & Data Collection | EXL to start Time and Motion study for all aligned resources post 3 months of steady state and report out baselined AHT data in case of major variation | Ranjan/Shikha | Sep 24 | Yet to start
 | EXL QA certification | EXL QA has been certified | Shikha / Ranjan | Jul 7 | Closed

## Slide 6: annexure

## Slide 7
Governance during steady state
Forum | Frequency (Suggested Timeline) | Activities | Participants | 
 |  |  | Prudential | EXL
Weekly Performance Review | Weekly | EXL Performance Review | Operations: Maria Lopes Joseph Bianco Patricia Waskiewicz | Operations: Kamesh Sharma Shikha Saini Ranjan Banerjee
Senior Leadership Service Delivery Overview | QBR | Review of monthly SLA performance | Vendor Management: Mark Smith Operations: Maria Lopes Joseph Bianco Patricia Waskiewicz | Account Management: Kunal Kapoor Operations: Kamesh Sharma Shikha Saini Ranjan Banerjee
Frequency of meetings & attendee list is subject to change as per Business requirement

## Slide 8
Proposed exl operating structure
Operations
Kamesh Sharma
Senior AVP - Operations
VP 2 - Operations
Ajay Singh
Ranjan Banerjee
Quality Auditors
Account Management
VP 2 – Account Management
Sarika Gupta
Shared resource
Dedicated resource
Quality & Process Excellence
Amit Srivastav
VP – QPE
Mohit Marwah
Sr Manager-QPE
Gulshan Kumar
Asst. Manager - QPE
Shikha Saini
Manager – Operations
Lead Asst. Manager - Operations
Senior AVP – QPE
Ashish Kumar Singh
VP –Account Management
Kunal Kapoor
Ops Associates (4 FTEs)
Dhirendra Singh
VP - Operations
GL Mailbox + Paper Mail

## Slide 9: Thankyou