## Home Page
Project Workbook
This project workbook is intended to function as a project control tool by consolidating project information including timelines, risk and action plan. Its' ease of use will aid in increased efficiency and communication between all project stakeholders
| For Discussion | For Information
Weekly Update Summary
Implementation Plan
Action Log
Application access status
Risk Log

## Implementation Plan
|  | Complete |  |  | WU/Convera
|  | On Schedule |  |  | Convera
Implementation Plan |  | At Risk |  |  | WU Activities
Delayed
Key tasks
WU - Accounts Payable |  | Not Due |  |  | Milestone
[5 empty] | Tollgate |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  |  | 2019-05-18
Task ID | Activities | Status | Duration (Days) | Planned Start Date | Planned End Date | Responsibility | time axis 2021-12-06 to 2022-10-31
1 | WU AP TRANSITION SUPPORT PLAN |  | 203 | 2021-12-06 | 2022-09-14
1.1 | PROGRAM LEVEL ACTIVITIES |  |  | 2021-12-06 | 2022-01-06
1.1 | Business Aware decision | Complete | 1 | 2021-12-06 | 2021-12-06 | WU/Convera | bar: 2021-12-06
1.2 | Project team to be identified | Complete | 1 | 2022-01-03 | 2022-01-03 | WU | bar: 2022-01-03
1.3 | Kick off meeting | Complete | 1 | 2022-01-06 | 2022-01-06 | WU | bar: 2022-01-03
2.1 | TRANSITION PLANNING & IT SET UP |  |  | 2021-12-06 | 2022-02-28
2.1 | Technology and Connectivity | Complete | 26 | 2021-12-06 | 2022-01-10 | WU | bar: 2021-12-06 to 2022-01-10
2.1.1 | User ID creation & testing | Complete | 7 | 2021-12-31 | 2022-01-10 | WU | bar: 2021-12-27 to 2022-01-10
2.1.2 | Enable currencies in global pay | Complete | 2 | 2022-01-10 | 2022-01-11 | WU | bar: 2022-01-10
2.1.3 | Test the payments, if the currencies are added | Complete | 1 | 2022-01-12 | 2022-01-12 | WU | bar: 2022-01-10
2.2 | VDI Connectivity for Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | Convera | bar: 2022-01-10 to 2022-01-17
2.2.1 | Move ERP to Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera | bar: 2022-01-10 to 2022-02-21
2.2.2 | All applications readiness to be confirmed in Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera | bar: 2022-01-10 to 2022-02-21
2.2.3 | Access to be provided in Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera | bar: 2022-01-10 to 2022-02-21
2.3 | Programming complete for Concur uploads | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.3.1 | Creating Convera upload file according to WUBS Convera convention by business | On Schedule | 36 | 2022-01-10 | 2022-02-28 | WU | bar: 2022-01-10 to 2022-02-21
2.3.2 | Access to WIN SCP | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.3.3 | Test WIN SCP | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.4 | Convera Concur instance live | On Schedule | 1 | 2022-01-14 | 2022-01-14 | Convera | bar: 2022-01-10
2.4.1 | Integrate EXL / WU in Convera Concur in new instance | On Schedule | 5 | 2022-01-10 | 2022-01-14 | Convera | bar: 2022-01-10
2.4.2 | Convera Concur ported to WD | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.4.3 | Creating Convera upload file according to WUBS Convera Concur convention by business | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.3 | Communication regarding AP uploads | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.3.1 | Upload agreements in accordance with Convera | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10
2.3.2 | Design internal audit requirement plan | On Schedule | 31 | 2022-01-10 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-21
2.4 | Design the Approval matrix | On Schedule | 29 | 2022-01-12 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-21
2.4.1 | Threshold limit based on designation | On Schedule | 29 | 2022-01-12 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-21
2.4.2 | Approval matrix for PO invoices | On Schedule | 24 | 2022-01-12 | 2022-02-14 | Convera | bar: 2022-01-10 to 2022-02-14
2.4.3 | Approval matrix for Non PO invoices | On Schedule | 24 | 2022-01-12 | 2022-02-14 | Convera | bar: 2022-01-10 to 2022-02-14
2.4.4 | Automatic work flow approval to be initiated based on desgination | On Schedule | 29 | 2022-01-12 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-21
2.4.5 | Communication to be sent to WU procurement team to stop adding PO in WU environment | On Schedule | 6 | 2022-02-07 | 2022-02-14 | WU | bar: 2022-02-07 to 2022-02-14
2.4.6 | Remove WUBS procurement access for WU employees | On Schedule | 1 | 2022-02-14 | 2022-02-14 | WU | bar: 2022-02-07 to 2022-02-14
2.5 | Banking info for new entities in Convera AP | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.5.1 | Costa Rica : Create a new bank account | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.5.2 | Canada :Create a new bank account | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.5.3 | India : Create a new bank account | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.5.4 | Lithuania : Make sure the bank account is operational | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.5.5 | Switzerland : Exisiting account available to be confirmed | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.5.6 | USA: Existing account available to be confirmed | On Schedule | 14 | 2022-01-12 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.6 | Communication regarding vendor invoicing to Convera | On Schedule | 27 | 2022-01-14 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-21
2.6.1 | Identify Convera personnel for real estate | On Schedule | 27 | 2022-01-14 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-21
2.7 | Status of Convera iProcure | On Schedule | 12 | 2022-01-14 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.7.1 | Interim process for WUBS PO intake | On Schedule | 12 | 2022-01-14 | 2022-01-31 | WU | bar: 2022-01-10 to 2022-01-31
2.7.2 | PO accrual process | On Schedule | 12 | 2022-01-14 | 2022-01-31 | WU | bar: 2022-01-10 to 2022-01-31
2.7.3 | Interim process for WUBS PO update | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10 to 2022-01-17
2.7.4 | Manual tracking of PO details | On Schedule | 5 | 2022-01-10 | 2022-01-14 | WU | bar: 2022-01-10 to 2022-01-17
2.7.5 | Retrive the category segments for PO | On Schedule | 16 | 2022-01-10 | 2022-01-31 | WU | bar: 2022-01-10 to 2022-01-31
2.8 | Convera AP ported to Work Day (WD) | On Schedule | 12 | 2022-01-14 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
2.9 | Convera Concur ported to Work Day (WD) | On Schedule | 12 | 2022-01-14 | 2022-01-31 | Convera | bar: 2022-01-10 to 2022-01-31
3 | TRANSITION EXECUTION |  |  | 2022-02-21 | 2022-02-24
3.1 | Process Documentation, review & Sign off | Not Due | 4 | 2022-02-21 | 2022-02-24 | WU | bar: 2022-02-21
3.2 | Operations Set Up - Quality process, SLA trackers | Not Due | TBD | TBD | TBD | Convera
4 | PARALLEL RUN EXECUTION |  |  | 2022-09-01 | 2022-09-05
4.1 | Go live | Not Due | TBD | TBD | TBD | WU
4.2 | Exit of TSA | Not Due | 3 | 2022-09-01 | 2022-09-05 | bar: 2022-09-05
4.2.1 | Tollgate 1: Exit of TSA | Not Due | 3 | 2022-09-01 | 2022-09-05 | WU | 2022-09-05: WU; 2022-09-12: Exit of TSA
5 | STABLISATION COMMENCEMENT |  |  | 2022-09-12 | 2022-09-12
5.1 | Hand Over to Operations | Not Due | 3 | 2022-09-12 | 2022-09-14 | WU | bar: 2022-09-12
5.1.1 | Tollgate 2: Handover to operations | Not Due | 3 | 2022-09-12 | 2022-09-14 | WU | 2022-09-19: Handover to Operations
Formulas:
WU Activities = MAX([WU Activities, row below]:G67)
TBD = MIN([TBD, row below]:F65)
TBD = NETWORKDAYS([TBD],[WU Activities])
Home
T
We are here
T1
Implementation Plan
T2

## Parallel Run Tollgate (hidden)
Go/ No Go Status Report - To start Parallel Run
Process: Accounts Payable | [6 empty] | Last updated on: | 2020-03-26
EXL Project Lead: Santosh Kumar
Western Union Project Lead:
Description |  | Score | Status |  |  | Sl. No. | Overall Status | No Go
Task or activity delayed, re-plan required, impacts other tasks |  | 0 | Red |  |  | 1 | Project - Commercial/ Communication / Governance | No Go
Task or activity delayed, recovery plan in place, due date still achievable |  | 1 | Amber |  |  | 2 | Organization & People | Go
Task or activity on track or complete, awaiting evidence of completion |  | 2 | Green |  |  | 3 | Knowledge Transfer (KT) / Training | No Go
Task or activity complete and evidence of completion received |  | 3 | Blue |  |  | 4 | Location, Infrastructure & Logistics | Go
Task or activity not applicable to current Transition, or not yet due to be started |  | NA | Gray |  |  | 5 | Process Scope & Design | Go with Action
Note: | [5 empty] | 6 | Reporting | No Go
1. The criteria will be updated following each Go/ No Go session, any section which has a No Go item will be classified as No Go overall. | [5 empty] | 7 | Quality and Compliance | No Go
2. For any item in Red or Yellow at the time of review, specific approval is required from the project stakeholders. All items incomplete would be included the following Go/No Go Toll-gate | [5 empty] | 8 | Business Continuity | Go with Action
[6 empty] | 9 | Technology | No Go
1 | Project - Commercial/ Communication / Governance | [5 empty] | Overall Status | No Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
1.1 | Program Management Template - Has program management reporting templates and communication/ governance plan been defined and agreed? | EXL |  | Project management reporting template is in place and used for weekly project discussions | No | 3 |  |  | Go
1.2 | Project Governance - Has regular project meeting scheduled as agreed in the governance document? | EXL and WU |  | Recurring project governance scheduled thrice a week (Mon, Wed and Fri), IT meetings scheduled twice a week and Steering Co. meeting is scheduled on every Thursday | No | 3 |  |  | Go
1.3 | Escalation Matrix: Has the process escalation matrix for ramp stage been agreed? | EXL and WU |  | Escalation matrix to be prepared, discussed and agreed with WU | No | 1 |  |  | Go with Action
1.4 | Communication plan and review meetings: Has the communication plan for parallel run / ramp phase and business review meetings to review performance planned and established? | EXL and WU |  | Communication plan for parallel run / ramp phase is part of project dashboard. Business review meeting to be scheduled | Yes | 1 |  |  | No Go
2 | Organization & People | [5 empty] | Overall Status | Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
2.1 | FTEs: Have the required number of FTE to commence Parallel run / ramp phase been hired? | EXL |  | All resources have been hired | Yes | 3 |  |  | Go
2.2 | Background check and drug test - Have the offshore resources completed the background check & drug test? | EXL |  | Background and drug test completed for offshore resources (external hires) | No | 3 |  |  | Go
2.3 | Ramp down plan: Has the FTE ramp-down plan at WU been determined? | WU |  | Due to COVID-19 WU may need to extend staff exit dates considering impact on training. WU to share revise ramp down plan | Yes | 1 |  |  | No Go
2.4 | SME Support: Is adequate SME support available from WU during Parallel run / Ramp ? | WU |  | WU to confirm if SME is available during Parallel run / Ramp | Yes | 2 |  |  | Go with Action
2.5 | Visa readiness - Have visas been applied and procured for WU SMEs travelling to EXL? | WU |  | Due to COVID-19, onsite travel is cancelled and remote training is conducted | Yes | NA
2.6 | Org. Structure: Has the retained organization at WU and Organization structure at EXL been defined, including operations and support staff? | EXL |  | Retained delivery organization structure has been defined | Yes | 3 |  |  | Go
3 | Knowledge Transfer (KT) / Training | [5 empty] | Overall Status | No Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
3.1 | Pre-Process training - Have EXL offshore resources completed the required Pre process training? | EXL |  | Pre-process training is completed | No | NA
3.2 | Knowledge transfer: Have the required number of EXL KT resources successfully completed training as per the curriculum and plan? | EXL and WU |  | Knowledge transfer is in-progress | Yes | 1 |  |  | No Go
3.3 | Offshore Training: Have the required number of EXL Offshore resources successfully completed training as per the curriculum and plan? | EXL |  | Knowledge transfer is in-progress | Yes | 1 |  |  | No Go
3.4 | Documentation: Have the detailed key stroke level SOPs been prepared by EXL and reviewed and approved by WU? | EXL and WU |  | Documentation is in-progress | Yes | 1 |  |  | No Go
3.5 | Assessments: Have the required number of EXL staff successfully completed the assessments as per approach and criteria agreed with WU? | WU |  | Training assessment will be conducted post completion of training | Yes | 1 |  |  | No Go
3.6 | Process updates - Has the process updates format agreed and deployed? | EXL and WU |  | Process update format to be agreed with WU | No | 1 |  |  | Go with Action
4 | Location, Infrastructure & Logistics | [5 empty] | Overall Status | Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
4.1 | Infrastructure: Has EXL completed the set-up of the operational infrastructure at agreed site ? | EXL |  | Operational infrastructure deployed at EXL site | Yes | 3 |  |  | Go
4.2 | Branding: Has WU provided EXL with branding requirements for service delivery locations? | WU |  | Trademark agreement for branding requirement shared by WU EXL to confirm if branding has been completed | No | 2 |  |  | Go
4.3 | Floor access: Have access to Operations floor been restricted to authorized EXL Personnel? | EXL |  | Operation floor access has been restricted to authorized personnel | No | 2 |  |  | Go
5 | Process Scope & Design | [5 empty] | Overall Status | Go with Action
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
5.1 | Scope: Have offshore process scope been revised (if applicable) for any changes post Knowledge Transfer and agreed? | EXL and WU |  | Offshore process scope has been identified and agreed. It is documented as part of Responsibility Matrix | No | 3 |  |  | Go
5.2 | Process Maps: Have the 'to be' process maps been prepared/ reviewed and approved by WU? | EXL and WU |  | All TO BE maps have been signed off by WU | Yes | 3 |  |  | Go
5.3 | FMEA: Has FMEA been prepared/ reviewed and approved by WU? | EXL and WU |  | FMEA yet to be prepared | No | 1 |  |  | Go with Action
5.4 | Workflow - Have workflow management processes been documented, agreed and tested between WU and EXL process owners? | EXL |  | Oracle workflow is used for invoice processing. For VM, T&E and Helpdesk requests which comes through email, tracking and reporting will be done manually | Yes | 3 |  |  | Go
5.5 | Responsibility Matrix: Has the responsibility split and outstanding issue resolution plan for Backlogs (non-routine items) and Work-In-Progress agreed? | EXL and WU |  | WU has agreed to resolve the existing non-routine backlog before EXL Go-live. Invoices put on hold by EXL to be EXL responsibility | Yes | 3 |  |  | Go
5.6 | Risks - Has the process specific risk and mitigation plan been discussed and updated? | EXL |  | Risk log is shared as part of the weekly project status | No | 3 |  |  | Go
6 | Reporting | [5 empty] | Overall Status | No Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
6.1 | Ramp plan: Has volume ramp up plan been agreed with WU? | EXL and WU |  | Volume ramp up plan to be discussed and agreed with WU | Yes | 1 |  |  | No Go
6.2 | Production reporting: Has ramp production reporting template agreed with WU? | EXL and WU |  | Ramp production reporting template to agreed with WU | Yes | 1 |  |  | No Go
6.3 | SLAs / KPIs: Have KPI's / SLA's metrics (including operational definition, frequency of distribution, data source, method of measurement) identified for baselining and signed-off? | EXL and WU |  | Though SLAs / KPIs are identified, operational definition, data source and method of measurement to be agreed with WU | Yes | 1 |  |  | No Go
6.4 | SLA reporting template: Has the template for SLA reporting been designed and agreed? | EXL and WU |  | Template for SLA reporting to be designed and agreed with WU | No | 1 |  |  | Go with Action
7 | Quality and Compliance | [5 empty] | Overall Status | No Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
7.1 | Quality approach: Has the quality framework and QC reporting format for offshore operations been agreed with WU? | EXL and WU |  | Quality framework and QC reporting format for offshore operations to be designed and agreed with WU | Yes | 1 |  |  | No Go
7.2 | Sampling methodology and %: Has the sampling methodology and sample percentage for transaction to be audited during parallel run / ramp agreed with WU ? | EXL and WU |  | Sampling methodology and sample percentage for transaction to be audited during parallel run / ramp to be agreed with WU | Yes | 1 |  |  | No Go
7.3 | Quality review: Has WU SMEs been identified to perform quality reviews? | WU |  | WU to confirm if SMEs are identified at their end for quality review | No | 1 |  |  | Go with Action
7.4 | Compliance: Has all legal and regulatory process requirements identified & confirmed compliance? | EXL and WU |  | MSA has been signed and covers the GDPR and other legal and compliance requirements. | No | 3 |  |  | Go
8 | Business Continuity | [5 empty] | Overall Status | Go with Action
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
8.1 | BCP plan: Has WU agreed and signed-off the process for business continuity during parallel run / ramp phase? | EXL and WU |  | EXL Bangalore is the alternate site for BCP In case of a disaster, operations will be recovered on a commercially reasonable best efforts basis from where the Services are being provided. Account level BCP plan and the relevant commercials will be agreed within 9 months after the Commencement Date | Yes | 3 |  |  | Go
8.2 | Critical activities - Has the list of critical activities and recovery time been identified and agreed? | EXL and WU |  | Critical activities and recovery time to be discussed and agreed | No | 1 |  |  | Go with Action
9 | Technology | [5 empty] | Overall Status | No Go
Ref. | Description | EXL and WU | Owner | Comments | Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
9.1 | Connectivity: Is End-to-End connectivity including voice solution established and tested at EXL location? | EXL |  | Connectivity established. WU has confirmed completion of application hosting within VDI. EXL to confirm voice solution enablement and testing | Yes | 1 |  |  | No Go
9.2 | Access provisioning - Have WU system and application IDs (including banks, other websites) been granted and shared with EXL offshore resources? | WU |  | All EXL users have access to Oracle. However access to IPM, WEC,OFR and other applications, shared drive, mailbox, websites etc. are being provisioned. | Yes | 0 |  |  | No Go
9.3 | UAT: Has UAT for VDI and applications access been conducted by EXL at offshore location? | EXL |  | All EXL users have access to Oracle. However access to IPM, WEC,OFR and other applications, shared drive, mailbox, websites etc. are being provisioned. | Yes | 0 |  |  | No Go
9.4 | Citrix licenses: Is Citrix stable with the required number of concurrent licenses available for offshore team? | WU |  | All users are able to login VDI, Oracle, MS Office applications, snipping tool, OKTA and Box access at the same time without any issue | Yes | 3 |  |  | Go

## Risk Log
Risk Log
Sl NO | Risk Category | Risk Description | Effect of Risk | Impact | Action to Mitigate | Risk Owner | Status | Target Resolution Date | Status Update
1 | Process | Vendor master creation of new entities | >>No information on volumes from new entities >>Can impact payments to the vendors | High | Vendor details for new entities is required | Convera | Open | 2022-01-17 | >>Complete vendor list & banking details are required as per Jally based on discussions in weekly connect dated 13/01/2022 | This comment needs to be rechecked
2 | Process | Approver matrix-Not received the approver list | >>Invoice will not be posted & settled in ERP | Medium | Convera to provide the details | Convera | Open | 2022-02-21
3 | Process | Segregation of Duties (SOD) | >>Team will only be able to process one functional area if SOD is applicable, Need additional resource in each functional area | Medium | As the team size is small, Segregation of duties might not be applicable at this stage but will be required at later stage | Convera | Open |  | >>Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13/01/2022.
4 | Process | Minimal information on volumes for new entities | >>If the volumes vary then there is possibility of backlogs | Medium | Team to review the volumes for next 2 months | WU | Open | 2022-02-01
5 | Process | Communication to vendors on WU-Convera separation | >>If the vendors are not informed then WU will continue to receive the invoices of Convera | Low | Vendors to be informed about the change & request them to provide invoices to WUBS (Convera) shared mail box | WU | Open |  | >>Mass communication is not required to vendors as per Joe based on discussions on weekly connect dated 13/01/2022. >>Currently there is a vendor work stream that is worked upon with Convera
6 | Process | Training on AP uploads to the requestor | >>If the requestor enters wrong GL code then system accepts the incorrect GL codes, hence it will impact the GL accounts. | High | >>Is there any mechanism where system does not allow the incorrect GL codes, this needs to be confirmed >>Train the requestors & provide them with the correct GL codes information | WU | Open | 2022-02-28 | >>Joe informed that this will remain between EXL & Convera as per discussions in weekly connect dated 13/01/2022. >>This topic needs to be part of Implementation plan as per Joe as per discussions in weekly connect dated 13/01/2022.
7 | Process | Duplicate checks are not performed | >>Chances of double payment from WU & Convera | High | Implement EXL’s fraudulent check tool | Convera | Open | 2022-02-28 | provide details by28feb whether this is not required or not
8 | Process | ACH payment method and check payment method : Positive pay file transfer to bank is not developed by IT in Convera system | >>Payment will not be not be settled for ACH & for bank will not be aware of cheques being issued | High | Technology team has to provide these details | IT | Closed |  | >>As per discussions by Joe on weekly call dated 13/01/2022, this risk item is closed. | Reasons required for closure
9 | Technology | Access to bank information | >> Not be able to check which payment has been settled and which payment has been returned | Medium | Payment file to be sent to treasury team so that they can release the payment | WU | Open |  | >>As per the update from Jally on weekly connect dated 13/1/2022, there is a back-up plan in place but EXL does not have access to bank details.
10 | Technology | IT communcation plan does not exist | >>Team will not be able to contact the technology related or IT related issues | High | Create an IT communication plan | WU / IT | Open |  | >>To check with Brian as per Joe based on discussions in weekly call dated 13/01/2022
11 | Technology | Concur login | >>If convera employees have access to WU Okta after close one | Low | Link to a website or log in page, password to be provided | WU / IT | Open | 2022-02-21
12 | Process | Final reconcillation of credit card transactions | >>Complete reconcillation is not possible, WU will have to handle this at a later stage | Medium | To monitor the unreconcilled expenses, | WU | Open |  | >> Currently the expense administration team will be monitoring this till the close of February as per weekly connect dated 13/01/2022.
13 | Technology | VDI access within the WU environment | >>Not able to review the accounts or invoices | High | VDI access to continue in WU environment during the TSA period | IT | Open |  | >>When VDI access moves to Convera environment, a VDI Convera access should be there. Needs to be confirmed with Brian. >>Jally informed that an MSA and SOW should be incorporated between Convera & EXL for IT team to provide access
14 | People | No buffer when it comes to count of resources | >>There are only 3 resources for this transition, if there is any attrition then it will impact the production. >>Transition could be delayed if there is attrition | Low | Currently assigned experienced resources hence buffer might not be required | WU | Open | 2022-02-01
15 | People | Shared resource for vendor management between WU & Convera | >>The resource has to work on both , we will not be able to use this resource in convera environment | High | Additional resource required for vendor management | WU / Convera | Open | 2022-02-28
16 | Technology | Single License | Only one resource has access to Vendor master | High | Additional access is required as there is a possibility that one resource can go on leave | Convera | Open | 2022-02-15 |  | More details required check with Jally

## Action Log
Action Log
# | Actions | Responsible | Target Completion | Status | Update / Comments (Month / Date)
1 | Finalize responsibility matrix | Both | 2022-01-21 | On Schedule
3 | Performance testing on ERP | WU | 2022-01-09 | Completed | Performance testing completed.
7 | Payment access is there or not needs to be verified for all resources | WU | 2022-01-14 | On Schedule
8 | Backlog: Pending invoices to be processed | WU | 2022-01-21 | On Schedule | >>Pending invoices are below 100 as on 17/01/2022.
9 | Cancel all credit cards of WUBS employees | WU | 2022-03-01 | On Schedule
10 | Terminate concur profiles of WUBS employees | WU | 2022-03-15 | On Schedule
11 | Vendor master creation of new entities(Risk) | Convera | 2022-02-15 | On Schedule | >>Lithuania vendor details are updated. >>Need the list of vendors to be created in Convera Oracle for India, Canada & CostaRica as on 17/01/2022. | more explanation is needed from Jally as the example cannot be mentioned in tracker
12 | Segregation of Duties (SOD) (Risk) | Convera | 2022-02-15 | On Schedule | >>Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13/01/2022.
13 | Communication to vendors on WU-Convera separation (Risk) | WU | 2022-02-15 | On Schedule | >>Mass communication is not required to vendors as per Joe based on discussions on weekly connect dated 13/01/2022. >>Currently there is a vendor work stream that is worked upon with Convera.
14 | Training on AP uploads to the requestor (Risk) | WU | 2022-04-30 | On Schedule | >>Joe informed that this will remain between EXL & Convera as per discussions in weekly call dated 13/01/2022. >>This topic needs to be part of Implementation plan as per Joe as per discussions in weekly connect dated 13/01/2022. >>This activity will remain ongoing.
15 | Access to bank information(Risk) : Not be able to check which payment has been settled and which payment has been returned | WU | 2022-02-15 | On Schedule | >>As per the update from Jally on weekly connect dated 13/1/2022, there is a back-up plan in place but EXL does not have access to bank details.
16 | IT communcation plan does not exist (Risk) :Team will not be able to contact technology related or IT related issues | WU | 2022-01-14 | Completed | >>To check with Brian as per Joe based on discussions on weekly connect dated 13/01/2022.Brian has provided these details hence marking it as complete.
17 | Final reconcillation of credit card transactions(Risk) :Complete reconcillation is not possible, WU will have to handle this at a later stage | WU | 2022-03-15 | On Schedule | >> Currently the expense administration team will be monitoring this till the close of February as per weekly connect dated 13/01/2022.
18 | VDI access within the WU environment (Risk) : Not able to review the accounts or invoices, to check VDI access to continue in WU environment during the TSA period |  | 2022-02-28 | On Schedule | >>When VDI access moves to Convera environment, a VDI Convera access should be there. Needs to be confirmed with Brian as per discussions in weekly call dated 13/01/2022. >>Jally informed that an MSA and SOW should be incorporated between Convera & EXL for IT team to provide access as per weekly connect dated 13/01/2022.
19 | Test the payments, if the currencies are added |  |  | Completed | >>Testing could not be completed on 12/01/2022. Retesting to be done on 13/01/2022 as per Jally based on discussions on weekly call dated 13/01/2022. >>The testing is completed & we were able to release the payment for multiple currencies, update as on 17/01/2022, hence marking this action as complete.
20 | 'Programming complete for Concur uploads: Status as to where we stand on Concur uploads |  | 2022-01-21 | On Schedule | >>Files are to be received on 13/01/2022 as per Rich based on discussions from weekly call dated 13/01/2022.
21 | Communication regarding AP uploads: Status of AP uploads(duplicating to 14 th cell |  | TBD | On Schedule | >>Carey informed that AP uploads are sent to Oracle Convera. Currently they are getting in and are getting processed for payments as per Carey on weekly call on 13/01/2022. However, there are certain minor exceptions. >>Access to WIN SCP is still pending to be recieved for team members as on 17/01/2022. | Carrey did not mention the minor exceptions hence take details from Jally
22 | Banking info for new entities in Convera AP access to Convera Bank accounts: Canada: Update on banks: Email received from Barclays Bank of Canada |  | 2022-02-28 | On Schedule | >>Email received from Barclays Bank as per 13/01/2022 as per Jally on weekly call dated 13/01/2022. >>Request sent to provide access to Helan, Thameem & Neethu. >>Current status as per Cassendra is that we are requesting for access to Convera Bank accounts for AP. >>EXL to just input the bank details, approver access to remain with Convera.
23 | To-be process maps for each process(check the deadline as per implementation plan) | WU | 2022-02-15 | On Schedule
24 | Citrix access needs to be changed to Convera environment | Convera | 2022-02-28 | On Schedule
25 | Reporting structure needs to be added | Convera | 2022-02-28 | On Schedule
33 | Convera Concur instance live |  | 2022-02-28 |  | think about it
35 | Convera Concur ported to WD |  | 2022-02-15
38 | Upload agreements in accordance with Convera |  | 2022-02-15
39 | Interim process for WUBS PO update |  | 2022-02-28
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59

## Application Status
|  | Last updated on 1/7/2022 IST 10:00 AM |  |  |  |  | Legend | Received | 100 | Pending | 25 | In-Progress | 75 | NA | 0
[5 empty] | Total Count | 10 | 40 | 40 | 40 | 40 | 35 | 30 | 30 | 5 | 35 | 40 | 30 | 27 | 25 | 32 | 9 | 32 | 23 | 37 | 40 | 20 | 8 | 8 | 40 | 8 | 3
|  | Updated by | Santosh Kumar |  | % Completion | 90% | 100% | 100% | 100% | 2.5% | 5.714% | 0% | 3.333% | 0% | 0% | 5% | 10% | 0% | -4% | -3.125% | 11.11% | -3.125% | -4.348% | 81.08% | 70% | -5% | 87.5% | 62.5% | 0% | 37.5% | 33.33%
[5 empty] | Pending Count | 1 | 0 | 0 | 0 | 39 | 33 | 30 | 29 | 5 | 35 | 38 | 27 | 27 | 26 | 33 | 8 | 33 | 24 | 7 | 12 | 21 | 1 | 3 | 40 | 5 | 2
|  | Resource Name & Role |  |  |  |  | Application Access Provisioning
|  | Name | SOW Job Title | Function Area | Location | WFH Capable/Tested | OKTA_ID | WU_Email ID | Oracle - Production | Concur | Noetix | Invoice Upload access | Onspring Ticketing tool | Workday | iProcurement | Shared Folder | Shared email box's | Taxport | WU Global Payables Supplier Maintenance | Payment Bank Accesses | Printer Access | WU Global Pay | Bank Of America | Citi Bank | Payment CAD-USD | Other Websites for Convera | Microsoft Office Application's | Snipping Tool | Reflection SFTP tool- WIN SCP | Box locator application | VDI Access in Convera
| 1 | Helan V A | Assistant Manager | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 25 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 2 | Thameem Meenatharakal K | Senior Associates | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 25 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 3 | Neethu Thomson | Senior Associates | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 25 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 4 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 5 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 100 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 6 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 5
| 7 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 0
| 8 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 9 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 10 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 11 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 12 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 13 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 0
100 | 14 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 15 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 16 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 17 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 18 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 19 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 75 | 0 | 0 | 0 | 75 | 75
| 20 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 21 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 22 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 23 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 24 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
| 25 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
| 26 |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 100 | 75 | 0
| 27 |  |  |  |  | 75 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 75 | 0 | 100 | 75 | 75 | 0
| 28 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 75 | 75 | 0
| 29 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 75 | 75 | 0 | 100 | 75 | 75 | 0
| 30 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 75 | 75 | 0 | 75 | 100 | 75 | 0
| 31 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 32 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 33 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 34 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 35 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 36 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 0 | 100 | 75 | 0 | 0 | 0 | 75 | 0
| 37 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 38 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 39 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 40 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
|  | Susan Paul | AVP | Service Delivery Lead | LAROC |  | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0

## Project Summary
Weekly Project Summary - As of Jan 17th, 2022
Project Name |  | WU_Convera AP Support |  |  | Project Stage
Overall Project Status |  | AMBER
Actual Completion |  | 51%
Target Completion |  | 51%
| Actual | Target (Variance) | Total
Completion | 51% | 0% | 49%
Discussion Points |  |  |  | "At Risk" or "Delayed" tasks
□ IT communcation plan does not exist:To check with Brian as per Joe based on discussions in weekly call dated 13/01/2022 |  |  |  | □
□ Segregation of Duties (SOD) :Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13/01/2022.
□ Banking info for new entities in Convera AP access to Convera Bank accounts: Canada: Update on banks: Email received from Barclays Bank of Canada
□
Project Updates |  |  |  | Task in Progress/ Activities planned for next week
PMO □ Payments will be done on Monday & Wednesday □ Process updates: □ Performance testing completed □ Backlog: Pending invoices to be processed:Pending invoices are below 100 as on 17/01/2022. □ Request sent to provide access to Helan, Thameem & Neethu for Banking info for new entities in Convera AP Technology □ □ □ □ □ □ |  |  |  | □ Backlog: Pending invoices to be processed :Pending invoices are below 40 as on 18/01/2022 □
Discussion / Decision taken
□ ACH payment method and check payment method is closed as per discussions with Joe on call dated 13/01/2022. □ IT communcation plan does not exist:To check with Brian as per Joe based on discussions in weekly connect dated 13/01/2022
Risk/Issue/ Challenges
□ Vendor master creation of new entities □ Single License □ Duplicate checks are not performed □ VDI access within the WU environment:Not able to review the accounts or invoices □ Training on AP uploads to the requestor □ Segregation of Duties (SOD) :>>Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13/01/2022. □ Final reconcillation of credit card transactions :Complete reconcillation is not possible, WU will have to handle this at a later stage
Actual Completion
Target Variance
B
Task completed
G
On target/ Progressing well
A
Need to fast track/ At Risk
R
Substantially delayed
Reason(s) for Variance, if Project Status is Red
Home
G
G
Home
A
A

## Sheet1 (hidden)
# | Action Item | Description | Action with | Target Date | Status
1
2
3
4
5
6
7
8
8a
9
10
11
12
13
14

## DD Tollgate (hidden)
Go/ No Go Status Report - To start Transition Planning
Process: Accounts Payable | [6 empty] | Last updated on: | 2020-02-10
EXL Project Lead: Deepak Bhoi
Western Union Project Lead: Carey Wood
Description |  | Score | Status |  |  | Sl. No. | Overall Status | Go with Action
Task or activity delayed, re-plan required, impacts other tasks |  | 0 | Red |  |  | 1 | Project - Commercial/ Communication / Governance | Go
Task or activity delayed, recovery plan in place, due date still achievable |  | 1 | Amber |  |  | 2 | Organization & People | Go
Task or activity on track or complete, awaiting evidence of completion |  | 2 | Green |  |  | 3 | Knowledge Transfer/ Training | Go
Task or activity complete and evidence of completion received |  | 3 | Blue |  |  | 4 | Location, Infrastructure & Logistics | Go
Task or activity not applicable to current Transition, or not yet due to be started |  | NA | Gray |  |  | 5 | Process Scope & Design | Go with Action
Note: | [5 empty] | 6 | Reporting | Go
1. The criteria will be updated following each Go/ No Go session, any section which has a No Go item will be classified as No Go overall. | [5 empty] | 7 | Compliance, Legal & Regulatory | Go
2. For any item in Red or Yellow at the time of review, specific approval is required from the project stakeholders. All items incomplete would be included the following Go/No Go Toll-gate | [5 empty] | 8 | Business Continuity | Go
[6 empty] | 9 | Technology | Go
1 | Project - Commercial/ Communication / Governance | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
1.1 | Has MSA/SOW been signed between Western Union & EXL? | Both |  | MSA/SOW signed off | No | 3 |  |  | Go
1.2 | Has Commercials(Pricing, Transition budget, Technology Cost) been finalized? | Both |  | WU has approved the budget for EUROC support and setting up a PO in this regard. Marginal rate increase FTE blended rate will be updated into the change order EXL will absorb the voice enablement cost (Voice mail and DID set up) cost | Yes | 3 |  |  | Go
1.3 | Has Transition plan / timelines been agreed with Western Union? | Both |  | Timelines advanced by 1 week and revised transition plan and approved as part of the DD report out approval by WU | Yes | 3 |  |  | Go
1.4 | Has the project plan with tasks, owners and milestones been defined/baseline and consistently tracked? | EXL |  | Detailed project plan is being tracked and status is being reported during the weekly project calls with Western Union | No | 3 |  |  | Go
1.5 | Has Project Team been identified at Western Union and EXL? | EXL / WU |  | Carey and a person from WU will work with EXL on IT implementation | No | 3 |  |  | Go
1.6 | Has Project risks and mitigation plans been defined and quantified? | EXL |  | Publised and discussed as part of the DD report out and project calls | No | 3 |  |  | Go
1.7 | Has Governance and Communication Plan been finalized and Has regular project meeting scheduled as agreed in the governance document? | Both |  | Governance and communication plan has been agreed Technology, Project calls and steering co. scheduled twice a week | No | 3 |  |  | Go
1.8 | Due Diligence Report Out and approval | EXL / WU |  | DD report out and discussion completed | Yes | 3 |  |  | Go
2 | Organization & People | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
2.1 | Has the skill-set assumptions validated for each process? | EXL |  | Skill set is part of Sow | No | 3 |  |  | Go
2.2 | Has job description been validated based upon skill-set and complexity of the processes? | EXL |  | Job description is part of Sow | No | 3 |  |  | Go
2.2 | Has the onshore and offshore delivery organization structure been agreed? | Both |  | Organization structure has been agreed and approved as part of the DD report out approval by WU | Yes | 3 |  |  | Go
3 | Knowledge Transfer/ Training | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
3.1 | Are there any training documentation and process maps available? | EXL |  | Desktop procedures available, they will be validated and refined during knowledge transfer | No | 3 |  |  | Go
3.1 | Has Knowledge Transfer approach (Knowledge transfer and parallel run duration) been finalized with Western Union? | Both |  | Knowledge transfer approach discussed and agreed | No | 3 |  |  | Go
4 | Location, Infrastructure & Logistics | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
4.1 | Has the delivery location been finalized? | EXL |  | Single Site, Kochi as it is the global hub for F&A | No | 3 |  |  | Go
4.2 | Has shift timings and hours coverage for EXL team agreed with Western Union? | Both |  | Shift design is part of SOW | No | 3 |  |  | Go
5 | Process Scope & Design | [5 empty] | Overall Status | Go with Action
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
5.1 | Has Process walkthrough / demo sessions completed to understand the process at high-level? | WU |  | Process walkthrough completed during the DD sessions | No | 3 |  |  | Go
5.2 | Has High level as-is process maps for each in-scope business process shared with Western Union? | EXL |  | As-Is process submitted for approval | No | 3 |  |  | Go
5.3 | Has existing workflow (if any) been assessed for work allocation, routing, tracking and approvals? | EXL |  | Oracle workflow is used for invoice processing. For VM, T&E and Helpdesk requests which comes through email, tracking and reporting will be done manually | No | 3 |  |  | Go
5.4 | Has High level to-be process maps for each in-scope business process shared with Western Union? | EXL |  | All approved except 2 (related to Concur) which are pending approval from WU | Yes | 2 | WU to approve 2 To-Be maps by 11th Feb | 2020-02-11 | Go with Action
5.5 | Has process scope (offshore/retained) been identified, documented and agreed? | Both |  | Process scope is part of the DD report out and has been approved by WU as part of the DD report out | Yes | 3 |  |  | Go
5.6 | Has FTE Scope been finalized (based on historical volume and effort data or Client to EXL FTE mapping) | Both |  | FTE scope finalized | Yes | 3 |  |  | Go
5.7 | Has To-Be workflow solution been finalized? | Both |  | VM T&E and Helpdesk request comes through email. Tracking and reporting is done manually | Yes | 3 |  |  | Go
6 | Reporting | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
6.1 | Has Performance management data gathering and baselining approach agreed and incorporated in MSA / Sow? | Both |  | EXL and WU have agreed on the majority of the standard SLAs, and for some of the SLAs, EXL will gather data for first 3 months from 100% go-live to baseline SLAs targets. Service credits for these SLAs will be applicable post baselining | Yes | 3 |  |  | Go
6.2 | Has historical volumes for at least one year in line with SLAs of the processes been assessed? | EXL |  | EXL has assessed the historical volume and the volumetric is shared as part of the DD report out | Yes | 3 |  |  | Go
6.3 | Has historical SLAs performance of the processes (formulas / calculation rules, data sources, impact of upstream / downstream processes or any other dependencies for meeting SLAs, reporting formats / frequencies / audience for SLA reports) been assessed? | EXL |  | Historical performance data assessed. Limited historical performance data available as most of the SLAs are not currently measured by WU. | Yes | 3 |  |  | Go
7 | Compliance, Legal & Regulatory | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
7.1 | Are there any legal restrictions/ licensing requirements, compliance, SOX, privacy requirements for processing in-scope transactions at EXL? If yes, has the approval been obtained to carry out these processes from offshore? | WU |  | MSA has been signed and covers the GDPR and other legal and statutory requirements. | Yes | 3 |  |  | Go
8 | Business Continuity | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
8.1 | Has BCP site strategy agreed? | Both |  | EXL Bangalore is the alternate site for BCP | No | 3 |  |  | Go
8.2 | Has the data for BCP requirement (current BCP plan, location, RTO, Hot / Warm Seats, Testing process) gathered? | EXL |  | In case of a disaster, operations will be recovered on a commercially reasonable best efforts basis from where the Services are being provided. Account level BCP plan and the relevant commercials will be agreed within 9 months after the Commencement Date | No | 3 |  |  | Go
9 | Technology | [5 empty] | Overall Status | Go
Ref. | Description | EXL / WU | Owner | Comments | On Critical Path ? | Status | Action Item (if status is Red or Yellow) | Target Date
9.1 | Are there any technological bottlenecks (Access restriction, licensing, Regulatory) that prevent offshoring? | WU |  | Access authorization may take longer for banking websites which will be resolved by WU in the access provisioning process. WU has confirmed that sufficient number of licenses are available | No | 3 |  |  | Go
9.2 | Has Technology and Telecom set-up duration agreed with technology team? | Both |  | Technology time has been proposed by EXL in the DD report out. This has been agreed and approved by WU during the IT project meeting | Yes | 3 |  |  | Go
9.3 | Has network connectivity, bandwidth requirements, desktop configuration (including dual screen or any specific requirements for sound cards or local hard drive) any other hardware or software requirements including licenses gathered? | Both |  | Requirement gathering has been completed | No | 3 |  |  | Go
9.4 | Has all the list of tools and applications and User ID creation process (lead time) been obtained? | Both |  | WU team confirmed the lead time for user ID creation and access provisioning ( 2 weeks). Application inventory finalized | Yes | 3 |  |  | Go
9.5 | Has high level Technology implementation plan been agreed with Western Union? | Both |  | Technology time has been proposed by EXL in the DD report out. This has been agreed and approved by WU during the IT project meeting | Yes | 3 |  |  | Go

## Issue Log (hidden)
Issue Log
Log # | Date | Category | Description of Issue | Priority | Owner | Status | Impact | Resolution | Comments | Target Resolution Date | Actual Resolution Date

## Dependencies (hidden)
Dependency Log
Log # | Date | Category | Description of Dependency | Resolved by | Priority | Owner | Comments | Closure Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14

## Process map status (hidden)
|  | As-Is Process maps |  |  |  | To-Be Process Maps
|  | EUROC |  |  |  | LAROC
Process | Location | Submitted | Date of Submission | Approved by | Approved Date | Submitted | Date of Submission | Approved by | Approved Date

## Process Risk Log (hidden)
Risk Log | [9 empty] | Risk Response Plan
Date Identified | Risk Category | Risk Description | Effect of Risk | Impact | Action to Mitigate | Risk Owner | Status | Target Resolution Date | Actual Resolution Date | Status Update
2020-02-17 | Process |  |  | Medium |  |  | Open | 2020-04-10
| Process |  |  | Medium |  |  | Open | 2020-04-10
| Process |  |  | High |  |  | Open | 2020-04-10
| Process |  |  | Medium |  |  | Open | 2020-04-10
| Process |  |  | Medium |  |  | Open | 2020-04-10
| Process |  |  | High |  |  | Open | 2020-04-17
| Process |  |  | Low |  |  | Open | 2020-04-17
| Process |  |  | High |  |  | Open | 2020-04-17
| Process |  |  | High |  |  | Open | 2020-04-17
| Process |  |  | High |  |  | Open | 2020-04-17
| Process |  |  | High |  |  | Open | 2020-04-17
| Process |  |  | Medium |  |  | Open | 2020-04-17
| Process |  |  | Medium |  |  | Open | 2020-04-17

## Governance & Comm. Plan (hidden)
WU and EXL - Governance Structure & Communication Plan
Program Level
Meeting | Purpose | Communication | Date |  | Time |  | Facilitator | WU | EXL
Attribute |  | Frequency | Start | End | Start | End |  | Participants | Participants
Quarterly Business Review/ Steering Committee | ■ Executive sponsorship and strategic objectives ■ Ensure alignment between business and outsourcing goals | Weekly | 2020-02-13 | TBD | 8 PM IST 7:30 AM MST | 8:30 PM IST 8:00 AM MST |  | Mark Hinsey Joseph St Denis Carey Wood Rich Pesa Brian Ross | Nikhil A., P. Ravi, Alex Abraham, Rishabh Jain, Susan Paul | ■ In person meetings ■ Quarterly Business Reviews ■ Program Performance / Strategy Reviews
Implementation Stage
Meeting | Purpose | Communication | Date |  | Time |  | Facilitator | WU | EXL
Attribute |  | Frequency | Start | End | Start | End |  | Participants | Participants
IT Enablement | ■Discuss progress on IT set up, connectivity & deployment ■Review and update “XYZ & EXL IT Action Log | Twice a week | 2020-01-06 | TBD | 10:30 PM IST 10:00 AM MST | 11:00 PM IST 10:30 AM MST | EXL IT Lead | Carey, Kris | IT Team Transition Manager Service Delivery Lead
Program Management | ■ Transition / Migration engagement supervision ■ Slippages against project plan, Issues & Risks ■ Pending issues and upcoming tasks ■ Communication, status reporting and escalation to steering committee | Thrice a week (Mon, Wed, Fri) | 2020-01-06 | TBD | 7:30 PM IST 7:00 AM MST | 8:00 PM IST 7:30 AM MST | Deepak Bhoi | Joe, Carey, Rich, Skirmante, Wagner | Alex Abraham Rishabh Jain Susan Paul Jally J Mampilly Mohd Naeem | ■ Monthly Business Reviews ■ Weekly SLAs / KPIs Performance TracK ■ Corrective Action Plan TracK ■ Volumes Forecasting / Planning
Go/No-go - Training Readiness | ■ Assess readiness to begin Production at offshore location ■ Risk identification and mitigation plan | Once | TBD | TBD | TBD | TBD | Deepak Bhoi | Joe, Carey, Rich, Skirmante, Wagner, Kris | Alex Abraham Rishabh Jain Susan Paul Jally J Mampilly Mohd Naeem
Go/No-go - Parallel Operations/Go-Live | ■ Assess readiness to begin Parallel Operations at EXL Delivery locations ■ Risk identification and mitigation plan | Once | TBD | TBD | TBD | TBD | Deepak Bhoi | Joe, Carey, Rich, Skirmante, Wagner, Kris | Alex Abraham Rishabh Jain Susan Paul Jally J Mampilly Mohd Naeem
Go Live / BAU Stage
Meeting | Purpose | Communication | Date |  | Time |  | Facilitator | WU | EXL
Attribute |  | Frequency | Start | End | Start | End |  | Participants | Participants
Operations Management & Performance Review | ■ Monitoring and reporting SLAs ■ Review all KPIs and Control metrics against established service levels ■ Discuss operational progress and challenges/ issues during pilot phase ■ Weekly review on pilot performance ■ Process Improvements | Daily/ Weekly | TBD | TBD | TBD | TBD | EXL Operations Manager | Carey, Rich | Account Manager Operations Manager Service Delivery lead Transition manager IT Lead | ■ Weekly / Daily SLAs / KPIs Performance TracK ■ Process Level Queries / Interaction as necessary
Business Review | ■ Overall health of the process ■ To review monthly performance summary, highlights/lowlights ■ Key Learnings and action plan for next month ■ Discussion open items | Monthly | TBD | TBD | TBD | TBD | Service Delivery Lead | Carey, Rich | Account Manager Operations Manager Service Delivery lead Transition manager IT Lead
Go/No-go - Final Milestone | ■ Assess readiness for Business as Usual ■ Key tasks accomplished & any pending issues | Once | TBD | TBD | TBD | TBD | Transition Manager | Carey, Rich | Account Manager Operations Manager Service Delivery lead Transition manager IT Lead