## Slide 1: Prudential Annuities BENE Services Transition – weekly program update
October 6, 2021
Confidential

## Slide 2
PRUDENTIAL Annuities BENE Services TRANSITION
Transition Status
SOW Execution
ES and SOW executed
Infra and Tech Readiness
Completed
Hiring – 10 FTEs (17 HC)
17 resources hired for the process:
15 external and 2 internal resources
2 QCAs included in the total headcount kept separate from the current ABS Transition SOW
Prudential ID Creation
Completed for all 17 resources
Pre Process Training
Completed for all 17 resources
Knowledge Transfer
RSA Validation, Follow Up Letters, APO and Lump Sum Training and nesting phase completed
Ramp
Sixth week of ramp phase in progress
KT = Knowledge Transfer
On Track
Delayed
Potential Delay
Completed
To be initiated
New Timeline
PP = Pre Process Training
Milestones | Jul’21 |  |  |  | Aug’21 |  |  |  |  | Sep’21 |  |  |  | Oct’21 |  |  |  | Nov’21 |  |  |  |  | Dec’21 |  |  | 
 | 05 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
Due Diligence |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SOW Execution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Infra and Tech Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prudential Id Creation and systems access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transition – Followup and RSA Validation (Training & Nesting) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transition – APO and Lump Sum Payments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Completed on 12th Feb
KT + Nesting
Ramp
Completed on 4th Jun
Completed on 1st Jun
Completed on 7th Jun
Completed on 9th Jul
Notes: 2 systems

## Slide 3
RAMP PERFORMANCE - PRODUCTION
PRODUCTION |  |  |  |  |  | 
 | Week of 30th Aug | Week of 6th Sep | Week of 13th Sep | Week of 20th Sep | Week of 29th Sep | Week of 6th Oct(Till
Follow-up Letters | 159 | 179 | 205 | 52 | 110 | 
RSA Validation | 90 | 91 | 320 | 247 | 0 | 
APO | 12 | 16 | 51 | 8 | 5 | 
Lump Sum | 115 | 105 | 48 | 182 | 61 | 
Production Counts - Total | 376 | 391 | 694 | 489 | 176 | 
Actual Productivity | 100% | 100% | 100% | 100% | 100% | 100%
Target Productivity | 30% | 40% | 50% | 60% | 70% | 80%
Actual Productivity is based on the volumes assigned to the team
Currently, majority of the volumes are being processed by EXL ABS team, onshore team is only supporting with a few Follow-up tasks and some exceptions

## Slide 4
RAMP PERFORMANCE - QUALITY
QUALITY |  |  |  |  |  | 
 |  | Week of 30th Aug | Week of 6th Sep | Week of 13th Sep | Week of 20th Sep | Week of 29th Sep (Till Mon)
Follow-up - Cases Reviewed |  | - | - | - | 82 | 50
Follow up - Total Errors |  | - | - | - | 2 | 1
Follow-up Quality % |  | - | - | - | 98% | 98%
RSA - Cases Reviewed |  | - | - | - | 212 | -
RSA - Total Errors |  | - | - | - | 5 | -
RSA Quality % |  | - | - | - | 98% | -
APO - Cases Reviewed |  | - | - | - | 52 | 5
APO - Total Errors |  | - | - | - | 6 | 0
APO Quality % |  | - | - | - | 88% | 100%
Lump Sum - Cases Reviewed |  | - | - | - | 118 | 22
Lump Sum - Total Errors |  | - | - | - | 25 | 5
Lump Sum Quality % |  | - | - | - | 79% | 77%
Total Audits |  | 423 | 284 | 468 | 461 | 77
Total Errors |  | 35 | 15 | 45 | 38 | 6
Quality Score |  | 92% | 95% | 90% | 95% | 92%
Target Quality |  | 82% | 85% | 88% | 90% | 92%

## Slide 5
RAMP PERFORMANCE - QUALITY
QUALITY |  |  |  |  |  | 
 | Week of 30th Aug | Week of 6th Sep | Week of 13th Sep | Week of 20th Sep | Week of 29th Sep (Till Mon) | 
Follow-up - Cases Reviewed | - | - | - | 82 | 50 | 
Follow up - Total Errors | - | - | - | 2 | 1 | 
Follow-up Quality % | - | - | - | 98% | 98% | 
RSA - Cases Reviewed | - | - | - | 212 | - | 
RSA - Total Errors | - | - | - | 5 | - | 
RSA Quality % | - | - | - | 98% | - | 
APO - Cases Reviewed | - | - | - | 52 | 5 | 
APO - Total Errors | - | - | - | 6 | 0 | 
APO Quality % | - | - | - | 88% | 100% | 
Lump Sum - Cases Reviewed | - | - | - | 118 | 22 | 
Lump Sum - Total Errors | - | - | - | 25 | 5 | 
Lump Sum Quality % | - | - | - | 79% | 77% | 
Total Audits | 423 | 284 | 468 | 461 | 77 | 
Total Errors | 35 | 15 | 45 | 38 | 6 | 
Quality Score | 92% | 95% | 90% | 95% | 92% | 
Target Quality | 82% | 85% | 88% | 90% | 92% | 

## Slide 6
OPEN ITEMS, ISSUES AND RISKS
S.No. | Open items | Next Steps | Responsibility | Target Date
1 | 3 team members to be certified to conduct Quality Audits for APO and RSA Validation | Quality Audit upskilling sessions started from 9/15, being conducted by Prudential Quality team | Prudential | TBD
2 |  |  |  | 
3 |  |  |  | 
OPEN ITEMS
S.No. | Open Risk | Action Plan | Responsibility | Target Date
1 | None |  |  | 
RISKS
S.No. | Open Issues | Action Plan | Responsibility | Target Date
1 | None |  |  | 
ISSUES

## Slide 7: Annexure

## Slide 8
Proposed ramp plan
Cases processed by EXL resources during initial weeks of ramp to be audited 100% by Prudential auditors and feedback to be provided within 24 hours to ensure processors are not making repeated errors
Percentage of claims reviewed by the coach will ramp-down as team members becomes more proficient in claims processing. Ultimately, the goal is to move to random auditing.
Final movement to random quality auditing will be determined by Prudential Supervisor and Analysts and will be based on individual performance
Checkpoint Tollgate to review the performance and declare steady state phase
EXL to share weekly ramp dashboard with Prudential stakeholders, covering performance snapshot of the team for previous week
Weekly Calibration call between Prudential & EXL teams to minimize knowledge gaps.
Weekly ramp performance review meeting between Prudential and EXL stakeholders to discuss performance and share feedbacks
Process | Metrics | Ramp Targets |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Follow up / Lump Sum Payments / APO / RSA | Productivity | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 95% | 95% | 98% | 100% | 100% | 100%
 | Quality | 80% | 82% | 85% | 88% | 90% | 92% | 94% | 95% | 95% | 96% | 96% | 97% | 97% | 97%
Week-by-Week targets for number of cases to be processed by EXL to be derived from target cases per hour provided by Prudential. No system generated report available to validate cases per hour processed by Prudential employees. To be validated during ramp phase
Targets to be adjusted in case of approved holidays
Assigned cases to be considered the target, in case if volumes received are lower than the targets
Governance During Ramp
Quality Audits during ramp and release framework

## Slide 9
Process training update WK 1 – ABS
On Track
Status |  |  | Jun 7th | Jun 8th | Jun 9th | Jun 10th | Jun 11th
Agenda | Planned |  | Introduction Icebreaker System Access Check Systems Navigation and Overview Overview of RSA Validation | RSA Validation Procedures Internal team huddle Debrief / Refresher | VPAS RSA Validation Process and Procedure Internal team huddle Debrief / Refresher | Introduction of LifeCad RSA Validation practice LifeCad RSA Validation Practice Internal team huddle Debrief / Refresher | Introduction of FAST RSA Validation Practice VPAS/LifeCad/ FAST RSA Validation Practice Internal team huddle, Debrief / Refresher
 | Actual | Completed | Introduction Icebreaker System Access Check Systems Navigation and Overview Overview of RSA Validation | RSA Validation Procedures Internal team huddle Debrief / Refresher | VPAS RSA Validation Process and Procedure Internal team huddle Debrief / Refresher | Introduction of LifeCad RSA Validation practice LifeCad RSA Validation Practice Internal team huddle Debrief / Refresher | Introduction of FAST RSA Validation Practice VPAS / LifeCad/ FAST RSA Validation Practice Internal team huddle, Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 10
Process training update WK 2 – ABS
On Track
Status |  |  | Jun 14th | Jun 15th | Jun 16th | Jun 17th | Jun 18th
Agenda | Planned |  | Annuities 101 Introduction to follow up letters, Purpose and objectives Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Solo) Internal team huddle Debrief / Refresher
 | Actual | Completed | Annuities 101 Introduction to follow up letters, Purpose and objectives Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Solo) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 11
Process training update WK 3 – ABS
On Track
Status |  |  | Jun 21st | Jun 22nd | Jun 23rd | Jun 24th | Jun 25th
Agenda | Planned |  | RPA BOT procedures RPA BOT procedures practice Internal team huddle Debrief / Refresher | Fast follow up letters Internal team huddle Debrief / Refresher | Lifecad follow up letters (Shadowing) Lifecad follow up letters (Solo) Internal team huddle Debrief / Refresher | Lifecad follow up letters (Solo) Internal team huddle Debrief / Refresher | VPAS/FAST/Lifecad follow up letters (Solo) RSA Validation processing Internal team huddle Debrief / Refresher
 | Actual | Completed | RPA BOT procedures RPA BOT procedures practice Internal team huddle Debrief / Refresher | Fast follow up letters Internal team huddle Debrief / Refresher | Lifecad follow up letters (Shadowing) Lifecad follow up letters (Solo) Internal team huddle Debrief / Refresher | Lifecad follow up letters (Solo) Internal team huddle Debrief / Refresher | VPAS/FAST/Lifecad follow up letters (Solo) RSA Validation processing Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 12
Process training update WK 4 – ABS
On Track
Status |  |  | Jun 28th | Jun 29th | Jun 30th | 1st Jul | 2nd Jul
Agenda | Planned |  | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher
 | Actual | Completed | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher | Follow up letter (solo) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 13
Process training update WK 5 – ABS
On Track
Status |  |  | Jul 5th | Jul 6th | Jul 7th | Jul 8th | Jul 9th
Agenda | Planned |  | Process Off | Follow up letter (solo) Internal team huddle Debrief / Refresher | RSA Validation (Solo) Internal team huddle Debrief / Refresher | RSA Validation (Solo) Internal team huddle Debrief / Refresher | Followup Letters and RSA Validation (Solo) Internal team huddle Debrief / Refresher
 | Actual | Completed |  | Follow up letter (solo) Internal team huddle Debrief / Refresher | RSA Validation (Solo) Internal team huddle Debrief / Refresher | RSA Validation (Solo) Internal team huddle Debrief / Refresher | Followup Letters and RSA Validation (Solo) Internal team huddle Debrief / Refresher
 |  | Pending |  | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 14
Process training update WK 6 – ABS
On Track
Status |  |  | Jul 12th | Jul 13th | Jul 14th | Jul 15th | Jul 16th
Agenda | Planned |  | Introduction of APO process, purpose and objectives Internal team huddle Debrief / Refresher | VPAS APO processing/ (Shadowing) Internal team huddle Debrief / Refresher | APO processing / (Solo) Internal team huddle Debrief / Refresher | APO processing / (Solo) Internal team huddle Debrief / Refresher | APO processing / (Solo) Internal team huddle Debrief / Refresher
 | Actual | Completed | Introduction of APO process, purpose and objectives Internal team huddle Debrief / Refresher | VPAS APO processing/ (Shadowing) Internal team huddle Debrief / Refresher | VPAS APO processing/ (Shadowing) Internal team huddle Debrief / Refresher | VPAS APO processing/ (Shadowing) Internal team huddle Debrief / Refresher | VPAS APO processing/ (Shadowing) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 15
Process training update WK 7 – ABS
On Track
Status |  |  | Jul 19th | Jul 20th | Jul 21st | Jul 22nd | Jul 23rd
Agenda | Planned |  | LifeCad APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | LifeCad APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | LifeCad APO Processing (Solo) AOS APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | VPAS/FAST/LifeCad APO Processing (Solo) Follow Up Letters Processing Internal team huddle Debrief / Refresher | VPAS/FAST/LifeCad APO Processing (Solo) Follow Up Letters Processing Internal team huddle Debrief / Refresher
 | Actual | Completed | LifeCad APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | LifeCad APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | LifeCad APO Processing (Solo) AOS APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | VPAS/FAST/LifeCad APO Processing (Solo) Follow Up Letters Processing Internal team huddle Debrief / Refresher | VPAS/FAST/LifeCad APO Processing (Solo) Follow Up Letters Processing Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 16
Process training update WK 8 – ABS
On Track
Status |  |  | Jul 26th | Jul 27th | Jul 28th | Jul 29th | Jul 30th
Agenda | Planned |  | Overview of good order requirements and claims form Death Certificate and beneficiary types Internal team huddle Debrief / Refresher | Claims option and claims requirements BPC notes templates Internal team huddle Debrief / Refresher | Due proof review and moving funds DCI and BOT Internal team huddle Debrief / Refresher | Outstanding checks in pride, Lump sum to receiving companies, Concierge and Platinum VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | NIGO, procedures, estimation, Child Support database searches VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher
 | Actual | Completed | Overview of good order requirements and claims form Death Certificate and beneficiary types Internal team huddle Debrief / Refresher | Claims option and claims requirements BPC notes templates Internal team huddle Debrief / Refresher | Due proof review and moving funds DCI and BOT Internal team huddle Debrief / Refresher | Outstanding checks in pride, Lump sum to receiving companies, Concierge and Platinum VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | NIGO, procedures, estimation, Child Support database searches VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 17
Process training update WK 9 – ABS
On Track
Status |  |  | Aug 2nd | Aug 3rd | Aug 4th | Aug 5th | Aug 6th
Agenda | Planned |  | Custodian, Lump sum on BCO TDA, Roth, IRA, minor beneficiaries Internal team huddle Debrief / Refresher | Manual Checks, Reversals, AIT fixes VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | Introduction of Lifecad Lump sum Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | PIP Contracts Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher
 | Actual | Completed | Custodian, Lump sum on BCO TDA, Roth, IRA, minor beneficiaries Internal team huddle Debrief / Refresher | Manual Checks, Reversals, AIT fixes VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | Introduction of Lifecad Lump sum Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | PIP Contracts Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 18
Process training update WK 10 – ABS
On Track
Status |  |  | Aug 9th | Aug 10th | Aug 11th | Aug 12th | Aug 13th
Agenda | Planned |  | APO/Lump sum practice (Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher
 | Actual | Completed | APO/Lump sum practice (Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 19
Process training update WK 11 – ABS
On Track
Status |  |  | Aug 16th | Aug 17th | Aug 18th | Aug 19th | Aug 20th
Agenda | Planned |  | APO/Lump sum practice (Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher
 | Actual | Completed | APO/Lump sum practice (Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher
 |  | Pending | None | None | None | None | None
On Track
1 Day behind
1+ Day behind

## Slide 20: Thank you