## Implementation Plan
|  | Complete |  |  | WU/Convera
|  | On Schedule |  |  | Convera
Implementation Plan |  | At Risk |  |  | WU Activities
Delayed
Key tasks
WU - Accounts Payable |  | Not Due |  |  | Milestone
[5 empty] | Tollgate |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  |  | 2019-05-18
Task ID | Activities | Status | Duration (Days) | Planned Start Date | Planned End Date | Responsibility | time axis 2021-12-06 to 2022-10-31
1 | WU AP TRANSITION SUPPORT PLAN |  | 203 | 2021-12-06 | 2022-09-14
1.1 | PROGRAM LEVEL ACTIVITIES |  |  | 2021-12-06 | 2022-01-06
1.1 | Business Aware decision | Complete | 1 | 2021-12-06 | 2021-12-06 | WU/Convera | bar: 2021-12-06
1.2 | Project team to be identified | Complete | 1 | 2022-01-03 | 2022-01-03 | WU | bar: 2022-01-03
1.3 | Kick off meeting | Complete | 1 | 2022-01-06 | 2022-01-06 | WU | bar: 2022-01-03
2.1 | TRANSITION PLANNING & IT SET UP |  |  | 2021-12-06 | 2022-02-28
2.1 | Technology and Connectivity | Complete | 26 | 2021-12-06 | 2022-01-10 | WU | bar: 2021-12-06 to 2022-01-10
2.1.1 | User ID creation & testing | Complete | 7 | 2021-12-31 | 2022-01-10 | WU | bar: 2021-12-27 to 2022-01-10
2.1.2 | Enable currencies in global pay | Complete | 2 | 2022-01-10 | 2022-01-11 | WU | bar: 2022-01-10
2.1.3 | Test the payments, if the currencies are added | Complete | 1 | 2022-01-12 | 2022-01-12 | WU | bar: 2022-01-10
2.2 | VDI Connectivity for Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | Convera | bar: 2022-01-10 to 2022-01-17
2.2.1 | Move ERP to Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera
2.2.2 | All applications readiness to be confirmed in Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera
2.2.3 | Access to be provided in Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera
2.3 | Programming complete for Concur uploads | Complete | 16 | 2022-01-10 | 2022-01-31 | WU | bar: 2022-01-10 to 2022-01-31
2.3.1 | Creating Convera upload file according to WUBS Convera convention by business | Complete | 36 | 2022-01-10 | 2022-02-28 | WU | bar: 2022-01-10 to 2022-02-28
2.3.2 | Access to WIN SCP | Complete | 10 | 2022-01-10 | 2022-01-21 | WU | bar: 2022-01-10 to 2022-01-17
2.3.3 | Test WIN SCP | On Schedule | 16 | 2022-01-10 | 2022-01-31 | WU | bar: 2022-01-10 to 2022-01-31
2.4 | Convera Concur instance live | On Schedule | 31 | 2022-01-14 | 2022-02-25 | Convera
2.4.1 | Onboard EXL / WU in Convera Concur in new instance | On Schedule | 35 | 2022-01-10 | 2022-02-25 | Convera
2.4.2 | Convera Concur feed into WD | On Schedule | 35 | 2022-01-10 | 2022-02-25 | WU
2.4.3 | Creating Convera upload file according to WUBS Convera Concur convention by business | Complete | 35 | 2022-01-10 | 2022-02-25 | WU
2.3 | Communication regarding AP uploads | On Schedule | 36 | 2022-01-10 | 2022-02-28 | Convera | bar: 2022-01-10 to 2022-02-28
2.3.1 | Upload agreements in accordance with Convera | On Schedule | 36 | 2022-01-10 | 2022-02-28 | Convera | bar: 2022-01-10 to 2022-02-28
2.3.2 | Design internal audit requirement plan | On Schedule | 31 | 2022-01-10 | 2022-02-21 | Convera
2.4 | Design the Approval matrix | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.4.1 | Threshold limit based on designation | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.4.2 | Approval matrix for PO invoices | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.4.3 | Approval matrix for Non PO invoices | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.4.4 | Automatic work flow approval to be initiated based on desgination | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.4.5 | Communication to be sent to WU procurement team to stop adding PO in WU environment | On Schedule | 11 | 2022-02-07 | 2022-02-21 | WU | bar: 2022-02-07 to 2022-02-21
2.4.6 | Remove WUBS procurement access for WU employees | On Schedule | 6 | 2022-02-14 | 2022-02-21 | WU | bar: 2022-02-07 to 2022-02-21
2.5 | Banking info for new entities in Convera AP | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.5.1 | Costa Rica : Create a new bank account | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.5.2 | Canada :Create a new bank account | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.5.3 | India : Create a new bank account | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.5.4 | Lithuania : Make sure the bank account is operational | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.5.5 | Switzerland : Existing account available to be confirmed | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.5.6 | USA: Existing account available to be confirmed | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.6 | Communication regarding vendor invoicing to Convera | On Schedule | 27 | 2022-01-14 | 2022-02-21 | Convera
2.6.1 | Identify Convera personnel for real estate | On Schedule | 27 | 2022-01-14 | 2022-02-21 | Convera
2.7 | Status of Convera iProcure | On Schedule | 26 | 2022-01-14 | 2022-02-18 | Convera | bar: 2022-01-10 to 2022-01-31
2.7.1 | Interim process for WUBS PO intake | On Schedule | 26 | 2022-01-14 | 2022-02-18 | Convera | bar: 2022-01-10 to 2022-02-14
2.7.2 | PO accrual process | On Schedule | 26 | 2022-01-14 | 2022-02-18 | WU | bar: 2022-01-10 to 2022-01-31
2.7.3 | Interim process for WUBS PO update | On Schedule | 30 | 2022-01-10 | 2022-02-18 | WU | bar: 2022-01-10 to 2022-02-14
2.7.4 | Manual tracking of PO details | On Schedule | 30 | 2022-01-10 | 2022-02-18 | WU | bar: 2022-01-10 to 2022-02-14
2.7.5 | Retrive the category segments for PO | On Schedule | 31 | 2022-01-10 | 2022-02-21 | Convera | bar: 2022-01-10 to 2022-02-14
2.8 | Convera AP feed from Work Day (WD) | On Schedule | 31 | 2022-01-14 | 2022-02-25 | Convera
2.9 | Convera Concur feed to Work Day (WD) | On Schedule | 31 | 2022-01-14 | 2022-02-25 | Convera
3 | TRANSITION EXECUTION |  |  | 2022-02-21 | 2022-02-24
3.1 | Process Documentation, review & Sign off | Not Due | 4 | 2022-02-21 | 2022-02-24 | WU | bar: 2022-02-21
3.2 | Operations Set Up - Quality process, SLA trackers | Not Due | TBD | TBD | TBD | Convera
4 | PARALLEL RUN EXECUTION |  |  | 2022-09-01 | 2022-09-05
4.1 | Go live | Not Due | TBD | TBD | TBD | WU
4.2 | Exit of TSA | Not Due | 3 | 2022-09-01 | 2022-09-05 | bar: 2022-09-05
4.2.1 | Tollgate 1: Exit of TSA | Not Due | 3 | 2022-09-01 | 2022-09-05 | WU | 2022-09-05: WU; 2022-09-12: Exit of TSA
5 | STABLISATION COMMENCEMENT |  |  | 2022-09-12 | 2022-09-12
5.1 | Hand Over to Operations | Not Due | 3 | 2022-09-12 | 2022-09-14 | WU | bar: 2022-09-12
5.1.1 | Tollgate 2: Handover to operations | Not Due | 3 | 2022-09-12 | 2022-09-14 | WU | 2022-09-19: Handover to Operations
Formulas:
WU Activities = MAX([WU Activities, row below]:G67)
TBD = MIN([TBD, row below]:F65)
TBD = NETWORKDAYS([TBD],[WU Activities])
T
We are here
T1
Implementation Plan
T2

## Action Log
Action Log
# | Actions | Responsible | Target Completion | Status | Update / Comments (Month / Date)
1 | Performance testing on ERP | WU | 2022-01-09 | Completed | >>Performance testing completed.
2 | Test the payments, if the currencies are added | WU | 2022-01-17 | Completed | >>Testing could not be completed on 12-Jan. Retesting to be done as per Jally based on discussions on weekly call dated 13-Jan. >>The testing is completed & we were able to release the payment for multiple currencies, update as on 17-Jan, hence marking this action as complete.
3 | Programming complete for Concur uploads | Rich_WU | 2022-01-21 | Completed | >>Files are to be received on 13-Jan as per Rich based on discussions from weekly call dated 13-Jan. >>Files went out last week.
4 | Access to WIN SCP | IT_WU | 2022-01-21 | Completed | >>Access to WIN SCP is still pending to be recieved for team members as on 17-Jan. Access to inbound folder is not received.
5 | Test WIN SCP | IT_WU | 2022-01-31 | On Schedule | >>Once all access are received then testing to done as per Jally on weekly call dated 20-Jan. Still issues faced support being taken up with WU IT team
6 | Convera Concur instance live Onboard EXL / WU in Convera Concur in new instance Convera Concur feed from WD | Andrey_Convera | 2022-02-25 | On Schedule | a). Convera to determine the process (pre and post Convera Concur instance) to provide the file to WU for payment of those expenses. b). This file will be submitted and processed through the AP TSA process (like all other invoices are submitted from specified Convera individuals). c).Convera request Access file from Rich to assist with this submission (WU to align internally to ensure no proprietary information is provided). Action item: Stuart Burwood to determine how to they will provide the file for T&E to be paid via the AP TSA process (pre and post set up of Convera Concur instance).
9 | Creating Convera upload file according to WUBS Convera Concur convention by business | Rich_WU | 2022-01-21 | Completed
10 | Communication regarding AP uploads, approvals &process flow | Andrey_Convera | 2022-02-28 | On Schedule | a). This process include recurring expenses associated with approved contracts (i.e. real estate, utilities, etc.) and will only need a pre-approval from Convera to proceed. Action item: Stuart Burwood to provide list of Convera individuals who can submit AP files for payment (from a WU perspective, these invoices have been approved to be paid).
11 | Upload agreements in accordance with Convera | Andrey_Convera | 2022-02-28 | On Schedule
12 | Interim process for WUBS PO update | Andrey_Convera | 2022-02-18 | On Schedule | a). POs will be cut off and closed within the WU system as of 3/25. b). WU will provide a listing of the open POs as of that date for Convera to manually track on their side.
13 | Manual tracking of PO details | Jally_EXL | 2022-02-18 | On Schedule | a). This topic remains an ongoing process as per Jally on weekly call dated 20-Jan. Currently this is not for EXL team members & is currently not required.
14 | Releasing of funds from bank account | Stuart_Convera/ Cassie_WU | 2022-01-27 | On Schedule | a). Convera to align internally to discuss on Thursday (1/27); and b). WU to align internally to discuss on Thursday (1/27). Will this continue to be Carey and Tammie with Convera Approval after Close 1? >>Action item: Stuart Burwood to discuss internally the funds release process to discuss on Thursday (1/27). >>Action item : Carey Wood, Joseph St Denis and Cassandra Lynn Sadusky to discuss internally the funds release process to discuss on Thursday (1/27). – Completed: Currently Carey approves funding for WUBS payments made, so we will need Convera approval step after close 1. >>Action item: Carey Wood and Cassandra Lynn Sadusky to confirm WUBS bank accounts to be used during the TSA for all countries. Carey to try and send morning of 1/26
15 | Banking info for new entities in Convera AP access to Convera Bank accounts: Canada: Update on banks: Email received from Barclays Bank of Canada >>Bank accounts needs to be created for Costa Rica, Canada & India >>Existing bank accounts should be confirmed for Switzerland & USA. | Chad_WUBS | 2022-02-25 | On Schedule | a). WU will confirm with WUBS treasury the current WUBS bank accounts used to pay AP today will be the same used during the TSA. b). Cassandra Sadusky and Carey Wood to discuss which bank accounts treasury (confirmed with Convera, Stewart and Andrey, treasury should make this decision) wants to use to pay invoices in the following countries (including who will obtain tokens and bank account access): i. Costa Rica; ii. Canada; iii. India; iv. US; and v. Switzerland
16 | Retrive the category segments for PO | WU_Jally & team | 2022-02-21 | On Schedule | Currently, this activity might not be onpriority atleast in the initial stages of the first day.
17 | Design the Approval matrix | Stuart_Convera | 2022-02-25 | On Schedule | There are few individuals who have been identified from Convera who will be submitting invoices. We can proceed to make payment

## Risk Log
Risk Log
Sl NO | Risk Category | Risk Description | Effect of Risk | Impact | Action to Mitigate | Risk Owner | Status | Target Resolution Date | Status Update
1 | Process | Vendor master creation of new entities | >>No information on volumes from new entities >>Can impact payments to the vendors | High | Vendor details for new entities is required | Andrey_Convera | Open | 2022-02-15 | >>Complete vendor list & banking details are required as per Jally based on discussions in weekly connect dated 13-Feb >>Convera support is required on this topic.
2 | Process | Approver matrix-Not received the approver list | >>Invoice will not be posted & settled in ERP | Medium | Convera to provide the details | Andrey_Convera | Open | 2022-02-21 | >>Convera support is required on this topic.
3 | Process | Segregation of Duties (SOD) | >>Team will only be able to process one functional area if SOD is applicable, Need additional resource in each functional area | Medium | As the team size is small, Segregation of duties might not be applicable at this stage but will be required at later stage | Andrey_Convera | Open | 2022-02-15 | >>Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13-Jan.
4 | Process | Minimal information on volumes for new entities | >>If the volumes vary then there is possibility of backlogs | Medium | Team to review the volumes for next 2 months | Carey_WU | Open | 2022-02-01
5 | Process | Communication to vendors on WU-Convera separation | >>If the vendors are not informed then WU will continue to receive the invoices of Convera | Low | Vendors to be informed about the change & request them to provide invoices to WUBS (Convera) shared mail box | Carey_WU/ Andrey_Convera | Open | 2022-02-15 | >>Mass communication is not required to vendors as per Joe based on discussions on weekly connect dated 13-Jan.. >>Currently there is a vendor work stream that is worked upon with Convera. Carey informed that they have added an new inbox on weekly call dated 20-Jan.
6 | Process | Training on AP uploads to the requestor | >>If the requestor enters wrong GL code then system accepts the incorrect GL codes, hence it will impact the GL accounts. | High | >>Is there any mechanism where system does not allow the incorrect GL codes, this needs to be confirmed >>Train the requestors & provide them with the correct GL codes information | Carey_WU | Open | 2022-04-30 | >>Joe informed that this will remain between EXL & Convera as per discussions in weekly connect dated 13-Jan. >>This topic needs to be part of Implementation plan as per Joe as per discussions in weekly connect dated 13-Jan. >>This activity remains ongoing.
7 | Process | Duplicate checks are not performed | >>Chances of double payment from WU & Convera | High | Implement EXL’s fraudulent check tool | Andrey_Convera | Open | 2022-02-28 | >>Needs to be confirmed by 28-Feb whether duplicate checks are required or not
8 | Process | ACH payment method and check payment method : Positive pay file transfer to bank is not developed by IT in Convera system | >>Payment will not be not be settled for ACH & for bank will not be aware of cheques being issued | High | Technology team has to provide these details | IT | Closed | 2022-01-13 | >>As per discussions by Joe on weekly call dated 13-Jan, this risk item is closed.
9 | Technology | Access to bank information | >> Not be able to check which payment has been settled and which payment has been returned | Medium | Payment file to be sent to treasury team so that they can release the payment | Andrey_Convera | Open | 2022-02-15 | >>As per the update from Jally on weekly connect dated 13-Jan, there is a back-up plan in place but EXL does not have access to bank details.
10 | Technology | IT communcation plan does not exist | >>Team will not be able to contact the technology related or IT related issues | High | Create an IT communication plan | WU / IT | Closed | 2022-01-14 | >>To check with Brian as per Joe based on discussions in weekly call dated 13-Jan. >>Brian has provided these details hence marking it as complete.
11 | Technology | Concur login | >>If convera employees have access to WU Okta after close one | Low | Link to a website or log in page, password to be provided | Rich_WU / IT | Open | 2022-02-21
12 | Process | Final reconcillation of credit card transactions | >>Complete reconcillation is not possible, WU will have to handle this at a later stage | Medium | To monitor the unreconcilled expenses, | Rich_WU | Open | 2022-03-15 | >> Currently the expense administration team will be monitoring this till the close of February as per weekly connect dated 13-Jan.
13 | Technology | VDI access within the WU environment | >>Not able to review the accounts or invoices | High | VDI access to continue in WU environment during the TSA period | WU / Convera IT | Open | 2022-02-28 | >>When VDI access moves to Convera environment, a VDI Convera access should be there. Needs to be confirmed with Brian. >>Jally informed that an MSA and SOW should be incorporated between Convera & EXL for IT team to provide access
14 | People | No buffer when it comes to count of resources | >>There are only 3 resources for this transition, if there is any attrition then it will impact the production. >>Transition could be delayed if there is attrition | Low | Currently assigned experienced resources hence buffer might not be required | Andrey_Convera | Open | 2022-02-01
15 | People | Shared resource for vendor management between WU & Convera | >>The resource has to work on both , we will not be able to use this resource in convera environment | High | Additional resource required for vendor management | Carey_WU / Andrey_Convera | Open | 2022-02-28
16 | Technology | Single License | Only one resource has access to Vendor master | High | Additional access is required as there is a possibility that one resource can go on leave | Andrey_Convera | Open | 2022-02-15 | >>Convera support is required on this topic.

## Application Status
|  | Last updated on 17-Jan IST 10:00 AM |  |  |  |  | Legend | Received | 100 | Pending | 25 | In-Progress | 75 | NA | 0
[5 empty] | Total Count | 10 | 40 | 40 | 40 | 40 | 35 | 30 | 27 | 8 | 35 | 40 | 27 | 27 | 25 | 35 | 6 | 32 | 23 | 40 | 37 | 23 | 8 | 8 | 40 | 8
|  | Updated by | Santosh Kumar |  | % Completion | 90% | 100% | 100% | 100% | 2.5% | 5.714% | 0% | 0% | 12.5% | 5.714% | 5% | 0% | 0% | -4% | 0% | 0% | -3.125% | -4.348% | 77.5% | 72.97% | 8.696% | 87.5% | 37.5% | 5% | 12.5%
[5 empty] | Pending Count | 1 | 0 | 0 | 0 | 39 | 33 | 30 | 27 | 7 | 33 | 38 | 27 | 27 | 26 | 35 | 6 | 33 | 24 | 9 | 10 | 21 | 1 | 5 | 38 | 7
|  | Resource Name & Role |  |  |  |  | Application Access Provisioning
|  | Name | SOW Job Title | Function Area | Location | WFH Capable/Tested | OKTA_ID | WU_Email ID | Oracle - Production | Concur | Noetix | Invoice Upload access | Workday | iProcurement | Shared Folder | Shared email box's | Taxport | WU Global Payables Supplier Maintenance | Payment Bank Accesses | Printer Access | WU Global Pay | Bank Of America | Citi Bank | Payment CAD-USD | Other Websites for Convera | Microsoft Office Application's | Snipping Tool | Reflection SFTP tool- WIN SCP | Box locator application | VDI Access in Convera
| 1 | Helan V A | Assistant Manager | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 2 | Thameem Meenatharakal K | Senior Associate | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 3 | Neethu Thomson | Senior Associate | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 4 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 5 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 100 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 6 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 5
| 7 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 0
| 8 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 9 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 10 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 11 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 12 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 13 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 0
100 | 14 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 15 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 16 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 17 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 18 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 19 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 75 | 0 | 0 | 0 | 75 | 75
| 20 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 21 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 22 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 23 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 24 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
| 25 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
| 26 |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 100 | 75 | 0
| 27 |  |  |  |  | 75 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 75 | 0 | 100 | 75 | 75 | 0
| 28 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 75 | 75 | 0
| 29 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 75 | 75 | 0 | 100 | 75 | 75 | 0
| 30 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 75 | 75 | 0 | 75 | 100 | 75 | 0
| 31 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 32 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 33 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 34 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 35 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 36 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 0 | 100 | 75 | 0 | 0 | 0 | 75 | 0
| 37 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 38 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 39 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 40 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
|  | Susan Paul | AVP | Service Delivery Lead | LAROC |  | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0

## Project Summary
Weekly Project Summary - As of 26-Jan
Project Name |  |  |  | Project Stage
Overall Project Status
Actual Completion
Target Completion
| Actual | Total
Completion | #REF! | #REF!
Discussion Points |  |  | "At Risk" or "Delayed" tasks
□ VDI Connectivity for Convera environment |  |  | □
□ Access to bank applications
□ Oracle single license for vendor master
□ Segregation of duties is applicable but not yet finalised
□ Convera Concur instance live
□ Approval matrix and approval threshold to be finalised for Convera (PO and Non PO)
□ Status of Convera iProcure
□ Convera AP / Concur ported to Work Day (WD)
Project Updates |  |  | Task in Progress / Activities planned for next week
PMO □ Payments will be done on Monday & Wednesday Process updates: □ Performance testing completed □ Completed all backlogs in invoice processing. □ Communication regarding AP uploads - On going □ Payments done in Convera Oracle environment for all vendors during this week □ Duplicate check done with the support of EXL fraudulent tool daily □ Quality check done on all invoices processed Technology Updates : □ Cash requirement report format updated and sign off provided □ Access received for WIN SCP - Inbound folder access yet to be configured |  |  | □ Segregation of Duties (SOD) : To check with Stuart for the status update on SoD as per weekly call dated 13-Feb. □ Testing for Convera India in progress for AP process. □ Access to inbound folder to be configured in WIN SCP. □ 1st soft close planned to be completed on 24th January 2022
Risk / Issue/ Challenges |  |  | Discussion / Decision taken
□ Vendor master creation of new entities □ Single License □ Duplicate checks are not performed □ VDI access within the WU environment:Not able to review the accounts or invoices □ Training on AP uploads to the requestor □ Segregation of Duties (SOD) :Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13-Jan. □ Final reconcillation of credit card transactions :Complete reconcillation is not possible, WU will have to handle this at a later stage |  |  | □ ACH payment method and check payment method is closed as per discussions with Joe on call dated 13-Jan. □ IT communcation plan does not exist:The request for communication plan to made with Brian based on discussions in weekly connect dated 13-Jan. Brian has provided the details for IT communication plan.
Actual Completion
Target Variance
B
Task completed
G
On target/ Progressing well
A
Need to fast track/ At Risk
R
Substantially delayed
Reason(s) for Variance, if Project Status is Red
G
G
A
A