## Slide 1
Knowledge Transfer Readiness Toll Gate
Accounts Payable and T & E
General Ledger

## Slide 2
Transition Methodology & approach
Outcomes
Finalize "To Be” state
Activities
Tollgate Review
Solution Design & Transition Set Up
Knowledge Transfer
Ramp Up/Parallel Run
Steady State
Knowledge acquisition and detailed documentation
Measure supervised performance against plan
As is documentation enabling standardization
Scope finalization
FTE validation
Hiring
IT solution design & implementation
Infrastructure setup
Pre-transition workshop to finalize transition roadmap, process maps & readiness for KT
Execute volume as per agreed ramp plan under BSWH supervision
Report on metrics
Root cause & action plan where required
Query and exception mgmt
Regular joint reviews and structured governance
Robust risk management
Complete pre process training
Complete job shadow
Prepare standard operating procedures (SOP)
Complete weekly knowledge assessments
Finalize volume ramp plan
Test IT & Infra readiness
Understand metrics & reporting
Business As Usual (BAU)
Independent production by EXL team
Report service levels & KPIs against contractual obligations
Set up operating governance
Create & execute improvement roadmap
Finalized to be solution
Validated Statement of Work
Finalized transition roadmap
Governance
Obtain sign-off on SOPs
Obtain sign off on FTE’s, metrics and service level framework
Parallel run readiness
Readiness for steady state
BAU operations
Steady state operating governance with BSWH
Tollgate Review
Tollgate Review
Tollgate Review
Focus of discussion, KT readiness for AP&TE and GL

## Slide 3
Transition Readiness Checklist (1/5)
2.0 Project Governance |  |  |  | General Ledger | AP&TE
Criteria | Owner | Status | Evidence | Remarks (if any) | Remarks (if any)
SOW Signed Compliance Review Process initiated | EXL | Pending | Signed SOW | 70% schedules closed, expected execution date in the week of 10/26 | 70% schedules closed, expected execution date in the week of 10/26
2.0 Project Governance |  |  |  | General Ledger | AP&TE
Agreed communication Plan (daily, weekly, monthly meetings) | EXL | Completed | Transition governance in place. Daily & weekly KT cadence to kick in from 10/26 |  | 
Agreed Escalation matrix | EXL | Completed | Organization structure mapping & escalation mechanism defined (to be developed at the lowest level during KT) |  | 
Agreed change management process | EXL | Completed | Changes captured from the last submission to the current program timelines, scope, FTE & commercials |  | 
Agreed project plan | EXL | Completed | Final program plan in place post the transition planning workshops |  | 
Risks, Actions, Issues and Dependencies documented and shared with all relevant stakeholders | EXL | Completed | RAID discussed as part of the program plan |  | 

## Slide 4
Transition Readiness Checklist (2/5)
3.0 Pre-process Training |  |  |  | General Ledger | AP&TE
Criteria | Owner | Status | Evidence | Remarks | Remarks
Pre-process roadmap created and agreed with relevant stakeholders | EXL | Completed | Agreed roadmap shared covering health care orientation, BSWH P&P’s & BSWH mandatory compliance trainings |  | 
Finalize KT model | EXL | Completed | Remote knowledge transfer to be conducted for all towers |  | 
Pre-process training completed for KT team | EXL | Pending | Pre-process training scores | In-progress, team in the process of completing compliance training shared by BSWH, to be completed by 10/23 | In-progress, team in the process of completing compliance training shared by BSWH, to be completed by 10/23
Day on day knowledge transfer plan drafted and agreed | EXL | Completed | Knowledge transfer in place for both AP & GL – Team to discuss the progress in the daily cadence and make shifts as needed |  | 
Training documentation completed (or a clear plan agreed if training documentation is not completed) | EXL | Pending | All key stroke level procedures will be prepared as part of the knowledge transfer phase |  | 
Training certification criteria finalized | EXL | Completed | Assessment criteria discussed. This would be a combination of verbal Q&A, live transaction completion by EXL under supervision |  | 

## Slide 5
Transition Readiness Checklist (3/5)
4.0 Process Management |  |  |  | General Ledger | AP&TE
Criteria | Owner | Status | Evidence | Remarks | Remarks
Process scope defined and agreed | EXL | Completed | Roles & responsibilities defined clearly across EXL & BSWH |  | 
FTE / Volumes assessment completed | EXL | Completed | FTE to FTE mapping completed as part of the solution workshops. Volumes to be baselined & any cascading impact to resourcing to be jointly discussed and agreed |  | 
To Be' process maps agreed | EXL | Pending | Approved process maps | High level process flows to be created as part of the knowledge transfer and completed by 11th Jan’21 | High level process flows to be created as part of the knowledge transfer and completed by 23rd Nov

## Slide 6
Transition Readiness Checklist (4/5)
5.0 People |  |  |  | General Ledger | AP&TE
Criteria | Owner | Status | Evidence | Remarks | Remarks
JD and Skill sets finalized | EXL | Completed | Skill sets & grade mix defined during solution workshops |  | 
Recruitment completed as required (including seeding) | EXL | Pending (GL) Completed (AP&TE) | Names shared | 32 resources on-boarded. 2 to be on-board by 28th Oct’21. 1 to be on-board by 2nd Nov 1 to be on-board by 16th Nov | 
Background checks completed | EXL | Pending | Background checks report shared | Approval for checks received on 10/19 Target completion date: 11/3 | Approval for checks received on 10/19 Target completion date: 11/3
Client SME identified and aligned for training | EXL | Completed | Confirmation email from client |  | 
Key operations leadership identified and aligned | EXL | Completed | Names shared |  | 
6.0 Transformation |  |  |  | General Ledger | AP&TE
Are there any upfront transformation commitment. Are the plans agreed to execute on transformation commitments. | EXL | Completed | Transformation workshops kicked off and key milestones defined | NA | 
Transformation governance framework established | EXL | Completed | Framework during governance to be part of the program update | NA | 

## Slide 7
Transition Readiness Checklist (5/5)
7.0 Technology and Telecom Setup |  |  |  | General Ledger | AP&TE
Criteria | Owner | Status | Evidence | Remarks | Remarks
User IDs created and tested for users as required | EXL | Completed | Confirmation on user id creation and testing | In-progress, to be completed before KT commencement | In-progress, to be completed before KT commencement
Access to client application remotely | EXL | Pending | Confirmation from technology teams | Access mapping under-way, publishing and testing expected to be completed in the week of 10/26 | Access mapping completed, publishing and testing expected to be completed by 10/23 & 10/26
8.0 Facility Setup |  |  |  | General Ledger | AP&TE
Space / Training Room identified at EXL location | EXL | NA | Confirmation on space. | Training to be conducted remotely due to WFH | Training to be conducted remotely due to WFH
Workstations installed as necessary | EXL | Completed | Confirmation email. | Workstations have been issued to all resources | Workstations have been issued to all resources
Note:
Additional 5 resources from FSSC to be part of the GL&AP trainings

## Slide 8: Annexure

## Slide 9
THE TEAM - GENERAL LEDGER
Susan Paul
Tower Lead
Corporate Services, Other Operations & Foundation + FA
Arun Prakasan
Lathikesh Kesavadas*
Angie Hutson
Project Lead
Laurie Hengst
Process Owner
Mike Bray
Process Owner
Corporate Services & Other Operations
CTX Hospitals & Clinics
DFW Hospitals
Health Texas
EXL Team
BSWH Team
Renee Troegel
Process Owner
Alex Abraham
Delivery Lead
Accounting Manager
Sr. Accountant
Accountant II
Accounting Assistant III
Financial Systems Associate
Manager
Team Lead
Sr. Accountant
Accountant I
Accountant II
Accounting Assistant
Financial Analyst
Accounting Manager
Accounting Team Lead
Accountant I
Accountant III
Financial Analyst
  Director
  Sr. Accountant
  Accountant I
  Accountant II
  Accounting Assistant
  Assistant II
Foundation Senior X 1
Director X 1
CTX Hospitals & Clinics + FA
Biju Nair*
Senior Manager
DFW Hospitals + FA
Rebadged profile to be confirmed by BSWH
Rebadged Resource
Wave | KT Start Date | Ramp Start Date | BAU start date
General Ledger | 10/26/2020 | 1/18/2021 | 4/19/2021
Jeremiah Johnson
Manager
Health Texas Clinics + FA
Manu Manuel
Abey George
Anas A M*
Ujjal Pankajakshan
Manager X 1
Sajith Pallath
Senior Manager
Sr. Accountant X 2
Accountant X 1
Leases
Sivaprasad Sreenivasan
Senior Manager
Research & Foundation
James Nash
Process Owner
Leases
Marcy Miles
Process Owner
15
Rebadged- 2
EXL Kochi- 13
12
Rebadged- 1
EXL Kochi- 11
6
Rebadged- 1
EXL Kochi- 5
9
Rebadged- 2
EXL Kochi- 7
Eldho George
Imthias Ameer
Rajesh Ramaswamy
Mohammed Safeer
Martin Varghese
Selvam Pandiyan
Sojan Mathew
Wilson Devassy
Nayana Ashok*
Carrie Theis
Process Owner
14
Retained
* Resource yet to be Onboarded

## Slide 10
THE TEAM – ACCOUNTS PAYABLE & T&E
Shibu Scariah
Tower Lead
Yashin Edison
Senior Manager
Molbin George
Lead Asst. Manager
(PO processing, Scanning
Kiran Joy
Asst. Manager
(Summary Bills, Reporting & Analysis)
Fiona Joan
Asst. Manager
(Disbursement)
Vidya Kumble
Asst. Manager
(Non PO processing)
Sr Associate X 4
Associate X 7
Sr Associate X 4
Associate X 2
Sr Associate X 1
Sr Associate X 1
Associate X 4
Angie Hutson
Project Lead
Alex Abraham
Delivery Lead
Dave Jenkin
Tower Lead
Cindy Novey
Process Owner
EXL Team
BSWH Team
AP Supervisors
T&E Program Specialist
Accounting Associate
Rebadged profile to be confirmed by BSWH
Sr Associate X 4
Associate X 8
Febin K A
Lead Asst. Manager
(Customer Support)
Customer Support X 1
Unclaimed property X 1
Rebadged Resource
Vendor Master X 2
Escalation Management
Wave | KT Start Date | Ramp Start Date | BAU start date
AP & TE | 10/26/2020 | 11/30/2020 | 1/11/2021
AP & TE -Reporting, Tax & Audit | 10/26/2020 | 11/30/2020 | 2/1/2021
T&E, Accounting, Tax Compliance and Audit Support
EXL Resources – 13
Rebadged - 1
EXL Resources – 13
Rebadged - 1
EXL Resources – 6
EXL Resources – 2
Rebadged - 2
EXL Resources – 7
EXL Resources – 3
Sr Associate X 1
Associate X 2

## Slide 11
General Ledger: governance Plan
Meeting | Objective | Participants | Frequency | Duration
Project Update | Review progress on knowledge transfer and ramp Resolve process and project level roadblocks Review risk log and address escalations Discuss and implement any quick win process improvement opportunity | BSWH – Mike Bray, Renee Troegel, Laurie Hengst, Carrie Theis & Trainers EXL – Sivaprasad S , Shagun. J (Transition manager), Sajith Paul, Arun Prakasan, Martin Varghese, Selvam Pandiyan, Eldho George, Imthias Ameer, Lathikesh Kesavadas, Manu Manuel | Daily | 30 minutes
Tower-Level Update | Track progress against the overall tower level transition plan Review exceptions to project plan and propose solutions Resolve any escalations / issues impacting project timelines Sign off on key tollgates for each process | BSWH – Mike Bray, Renee Troegel, Laurie Hengst, Carrie Theis EXL – Susan Paul , Abhay M | Weekly | 30 minutes
Weekly Transition Governance | Update on progress against transition plans and milestones Decide on and uphold all key design principles Ensure adequate resource availability to support transition or transformation efforts To address any programme level risks and issues or unresolved items from the tower governance Key decisions and approve any deviations (via formal change control template) | BSWH – Bethany. F (Program Director), James. P, Angie.H, EXL – Nikhil D (Client Partner), Jordan A (Account mgmt.), Alex A (Service delivery lead), Rishabh J (Account mgmt.), Susan P, Abhay M (Transition lead), | Weekly (Friday) | 60 minutes

## Slide 12
AP&TE: governance Plan
Meeting | Objective | Participants | Frequency | Duration
Project Update | Review progress on knowledge transfer and ramp Resolve process and project level roadblocks Review risk log and address escalations Discuss and implement any quick win process improvement opportunity | BSWH – Dave Jenkin, Cindy Novey, Charlynn Mader, Denice Bucher, Josh Middendorf, Michelle Ivanosvsky, Deborah Sniggs, April Spoon and Susan Manor EXL – Yashin E, Shagun John(Transition manager), Febin K A, Molbin George, Fiona Joan, Kiran Joy and Vidya Kumble | Daily | 30 minutes
Tower-Level Update | Track progress against the overall tower level transition plan Review exceptions to project plan and propose solutions Resolve any escalations / issues impacting project timelines Sign off on key tollgates for each process | BSWH – Dave Jenkin EXL – Yashin Edison, Shibu Scariah, Abhay M | Weekly | 30 minutes
Weekly Transition Governance | Update on progress against transition plans and milestones Decide on and uphold all key design principles Ensure adequate resource availability to support transition or transformation efforts To address any programme level risks and issues or unresolved items from the tower governance Key decisions and approve any deviations (via formal change control template) | BSWH – Bethany. F (Program Director), James. P, Angie.H, Dave Jenkin EXL – Nikhil D (Client Partner), Jordan A (Account mgmt.), Alex A (Service delivery lead), Rishabh J (Account mgmt.), Shibu Scariah, Abhay M (Transition lead) | Weekly (Friday) | 60 minutes

## Slide 13
Transformation: governance Plan
Meeting | Objective | Participants | Frequency | Duration
Project Update | Review progress on solution implementation of vendor statement reconciliation Resolve project level roadblocks Resolve any escalations / issues impacting project timelines Sign off on key milestones for each process | BSWH – Dave Jenkin, Cindy Novey, Charlynn Mader, April Spoon, Marc B, Dorothy C EXL – Suri Babu K, Shibu Scariah, Ramnath S, Muhammed P, Yashin E, Shagun John(Transition manager), Febin K A | Weekly | 15 minutes
Weekly Transition Governance | Update on progress against transition plans and milestones Decide on and uphold all key design principles Ensure adequate resource availability to support transition or transformation efforts To address any programme level risks and issues or unresolved items from the tower governance Key decisions and approve any deviations (via formal change control template) | BSWH – Bethany. F (Program Director), James. P, Angie.H, Dave Jenkin EXL – Nikhil D (Client Partner), Jordan A (Account mgmt.), Alex A (Service delivery lead), Rishabh J (Account mgmt.), Shibu S, Abhay M (Transition lead), Suri Babu K, Ramnath S | Weekly (Friday) | 60 minutes

## Slide 14
General Ledger- Escalation Matrix
BSWH - CTX Hospitals & Clinics + FA, Health Texas Clinics + FA, Leases |  | 
Level 1 | Level 2 | Level 3
Name: TBD Designation: Cluster Managers Email : TBD | Name: Mike Bray, Laurie Hengst,Carrie Theis Designation: Process Owners Email : Mike.Bray@BSWHealth.org Renee.Troegel@BSWHealth.org Laurie.Hengst@BSWHealth.org James.Nash@BSWHealth.org Carrie.Theis@BSWHealth.org | Name: Angie H, Designation: Project Lead Email : Angie.Hutson@BSWHealth.org
EXL- CTX Hospitals & Clinics + FA, Health Texas Clinics + FA, Leases |  |  |  | 
Team | Level 1 | Level 2 | Level 3 | Level 4
Service Delivery | Name: Martin Varghese, Eldho George, Manu Manuel, Arun Prakasan Designation: Cluster Managers Email : Martin.Varghese@exlservice.com Eldho.George@exlservice.com Manu.Manuel@exlservice.com Arun.V@exlservice.com | Name: Sivaprasad S., Sajith Pallath Designation: Process Owner Email : Siva.S@exlservice.com Sajith.Pallath@exlservice.com | Name: Susan P Designation: Tower Lead Email: Susan.Paul@exlservice.com | Name: Alex A Designation: Delivery Lead Email : Alex.Abraham@exlservice.com
Transition | Name: Shagun J Designation: Project Manager Email : Shagun.John@exlservice.com | Name: Shagun J Designation: Project Manager Email : Shagun.John@exlservice.com | Name: Abhay M Designation: Project Lead Email : Abhay.Mehta@exlservice.com | Name: Bal G Designation: Transition Lead Email : Bal.Gupta@exlservice.com

## Slide 15
AP&TE- Escalation Matrix
BSWH |  | 
Level 1 | Level 2 | Level 3
Name: TBD Designation: Team Supervisors Email : xx | Name: Cindy. N & Dave Designation: Director & VP - AP & T&E Email : David.Jenkins@BSWHealth.org Cindy.Novey@BSWHealth.org | Name: Angie H Designation: Project Lead Email : Angie.Hutson@BSWHealth.org
EXL |  |  |  | 
Team | Level 1 | Level 2 | Level 3 | Level 4
Service Delivery | Name: Febin, Molbin, Kiran, Fiona & Vidya Designation: Team Supervisors Email: Febin.AbdulSalim@exlservice.com Molbin.J@exlservice.com Kiran.Joy@exlservice.com Fiona.Pereira@exlservice.com Vidya.Kumble@exlservice.com | Name: Yashin E Designation: Senior Manager Email : Yashin.Edison@exlservice.com | Name: Shibu S Designation: Tower Lead Email: Shibu.Scaria@exlservice.com | Name: Alex A Designation: Service Delivery Lead Email : Alex.Abraham@exlservice.com
Transition | Name: Shagun John Designation: Project Manager Email : Shagun.John@exlservice.com | Name: Shagun John Designation: Project Manager Email : Shagun.John@exlservice.com | Name: Abhay M Designation: Project Lead Email : Abhay.Mehta@exlservice.com | Name: Bal G Designation: Transition Lead Email : Bal.Gupta@exlservice.com

## Slide 16
Day-wise Knowledge Transfer Plan
Category | Queries/ Questions/ Recommendations
Training Plan | We compared between Training plan and Close checklists for each of the hubs Tried mapping various activities to ensure that all activities in the checklist are covered in the training plan We came across few activities which did not find a place in the training plan For example there are 15 Activities in the DFW Hospital checklist which cannot be mapped to the KT plan list Are they going to be retained by BSWH or to be handled by Rebadged resources If Foundation Accounting is going to be managed by Rebadged resources, do we need to plan Week 6&7 (row #128 to 135) for Foundation Accounting- Can we remove those activities which are not required to be trained Fixed Asset Accounting – Can we move it to Week 2&3 Row 60- No specific Training Day or Trainer or Topic assigned
Training Time | Week 1, 2 and 3 are going to be overview sessions held by Directors; Week 4 and 5 are blackout dates. So the specific GL process trainings (row 34) will start only from week 6 &7 which is shown as OBS – recommend that we start specific training from Week 3 so that EXL team has enough knowledge work to do revision during blackout dates (Week 3 – from Thursday of week 3) There are close to 28 accrual entries in DFW H, like wise for each of the Hubs – But we could only see one line item (row 60) for accrual and is mentioned as ‘Include in General Training’. So does this cover for all accruals? Recommendation to plan for trainings for standalone processes like Stats, missing activities from checklist as mentioned in 3 above in week 3 and 4 Recons training duration seem to be only in week 8 (row 148)- For 11000 recs it may not be enough time- recommend we keep at least 2-3 weeks to go through each rec under each Hub to at least discuss the purpose, input, open items etc. Training durations and dates to be added for all the activities mention where there are no dates and Trainers – Row# 55 to 63 Recommend to keep at least 2 weeks after week 6&7 for Practice cases, Simulations, Query clarification, Recap sessions and Assessments time
Hands On Practice | When do we plan to do hands on practices and Who would be auditing the practice / live cases during the KT phase; we can plan for simulation exercises and ensure we do the complete close checklist at least once during week 7,8 & 9 To discuss the plan for First ramp close – what is the percentage expected to be taken by EXL in January close in February
Process Documentation | Can EXL team get access to all the existing JE from Image Now – at least for 6 months of historical data to get an understanding of the supporting documentation Names of the SMEs/ Trainers who would be reviewing and signing off the process maps and SOPs
Others | Clear demarcation required on the activities which will be performed by EXL/ Rebadged resources/ BSWH retained staff

## Slide 17
AP Day-wise Knowledge Transfer Plan
Category | Recommendations
Training Time | Hands on practice to be planned for all activities in Sandbox/ Live environment Shadowing of the process wherever possible and if can be planned and incorporated to the KT plan Practice cases, Query clarification, Recap sessions and Assessments time to be baked-in in the training plan for all the tasks the teams are getting trained
Hands On Practice | Support required by BSWH SME to review cases worked by EXL team Daily volumes to be agreed for hands-on practice, to be increased gradually
Process Documentation | All SOPs/documents to be signed-off before ramp commencement, signing authority to be agreed with BSWH
Others | Clear demarcation of activities/volumes which will be performed by EXL/ Rebadged resources/ BSWH retained staff
Process level snap-shot of KT Plan

## Slide 18
Particulars | Future State FTE | 2020 |  |  |  |  | 2021 |  |  | 
Sub Process | Total FTE# | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
DFW Hospitals & Clinics | 36 |  |  |  |  |  |  |  |  | 
CTX Hospitals & Clinics |  |  |  |  |  |  |  |  |  | 
Health Texas |  |  |  |  |  |  |  |  |  | 
Corporate Services |  |  |  |  |  |  |  |  |  | 
Other operations |  |  |  |  |  |  |  |  |  | 
General Ledger: Implementation Plan
Ramp Up
Volume initiation @ EXL
Stabilization
Remote Training
Pre Process Training
Hiring
Go live date for Rebadged employees
Black out and holiday period
12 W
13 W
3 W
7 W
12 W
13 W
3 W
7 W
12 W
13 W
3 W
7 W
12 W
13 W
3 W
7 W
12 W
13 W
3 W
7 W
Transition Change Log
Considered black-out , holidays and month close weeks, duration of KT and Ramp were increased to 12 and 13 weeks respectively (previously it was 8 and 12 wk.) with BAU in April

## Slide 19
Particulars | Current State FTE | Future State FTE |  |  | 2020 |  |  |  |  | 2021 | 
Sub Process | BSWH Dallas | EXL Onsite | EXL Kochi | Total FTE# | Aug | Sep | Oct | Nov | Dec | Jan | Feb
AP Strategy. Policy Set up & Acquisitions and Divestitures | 2 | - | - | 2 |  |  |  |  |  |  | 
Vendor Set up | 1 | 2 | - | 3 |  |  |  |  |  |  | 
Scanning | 1 | - | 1 | 2 |  |  |  |  |  |  | 
PO Invoice processing Non PO Invoice processing Summary Bills Patient Refunds | 3 | - | 19 | 22 |  |  |  |  |  |  | 
T&E Expense Process/Audit | 2 | - | 1 | 3 |  |  |  |  |  |  | 
Disbursements | 2 | - | 2 | 4 |  |  |  |  |  |  | 
Customer Support | 2 | 1 | 16 | 19 |  |  |  |  |  |  | 
>Reporting and Analysis >Tax Compliance >Audit Support | - | - | 7 | 7 |  |  |  |  |  |  | 
Accounting | - | - | 1 | 1 |  |  |  |  |  |  | 
Unclaimed Property | - | 1 | - | 1 |  |  |  |  |  |  | 
Ramp Up
Volume initiation @ EXL
Stabilization
Remote Training
Pre Process Training
Hiring
Go live date for Rebadged employees
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
5 W
6W
4 W
4 W
Black out and holiday period
Transition change log
All sub processes areas the knowledge transfer duration increased by1 week and ramp by 2 weeks, black-out and holidays factored
Ramp duration increased by further 3 weeks for 7 FTE's (Reporting & analysis sub group)
AP & T&E: Implementation Plan
Total FTEs | 13 | 4 | 47 | 64
5 W
9W
4 W
4 W
47 EXL Kochi FTE – Includes 3 FTEs benefit expected from transformation

## Slide 20
Roles and Responsibilities during Knowledge Transfer
Stage | BSWH Responsibility | EXL Responsibility | Success Criteria
Kick-Off | Assist EXL team with logistics and access to client network/relevant applications Review training plan and suggest refinements | Test application access Start monitoring on a daily basis | Quick set-up & training readiness Clear training roadmap
Training/ Work Shadowing | Provide EXL with an overview of the process you support as well as your specific role within the process (key process steps, up/down stream linkages, applications used, etc..) Conduct day-to-day activities while trainee observes; explain process steps as you perform them Participate in morning Q&A sessions to answer questions as needed As appropriate allow trainees to perform tasks and observe, to gain confidence | Ensure adherence to the training plan, flag any major deviations Ask probing questions as required to enable process understanding As appropriate, perform tasks under Trainer supervision | Effective knowledge transfer to maintain project timeline & quality
Hands-on Practice | Provide appropriate test environment, with access to all applications Provide access to production environment Audit practice cases or Live cases ( in the absence of test environment) and share feedback with the team | Practice activities covered during the day’s training in test environment, with a view on process documentation As appropriate perform tasks under Trainer supervision Master process steps to able to perform tasks in production environment | Gradual progression towards performing tasks independently
Process Documentation | Finalize list of SOPs Review SOP (Standard Operating Procedure) document for accuracy; edit jointly with EXL as required Final sign-off on SOPs | Propose list of SOPs to be created, monitor completion Document process steps as described by Trainers and create SOPs Review content of SOP (SIPOCs, Process Flows, etc..) with Trainers for accuracy | Comprehensive and accurate documentation
KT Assessment | Develop questionnaire/test and conduct weekly assessment to evaluate process understanding by EXL Develop final assessment questionnaire/test to provide criteria for go-live | Complete the assessment within defined time period; scoring above desired threshold EXL employees undergo final assessment; facilitated by BSWH trainers | EXL pass rate above desired quality thresholds

## Slide 21
KNOWLEDGE TRANSFER APPROACH
Pre-Process Training
Health care orientation
High skilled and experienced staff to be seeded for BSWH knowledge transfer
All recorded sessions and documentation shared by BSWH will be made available to the teams
Sandbox environment for the staff to get familiarize with the key system /ERP
Theoretical
Activity overview – what is the objective, why this activity is done
Activity lifecycle – inputs to process to output
Existing SOPs
Training for each process typically goes through six different steps for an effective knowledge transfer
Job shadow/ demonstrations
Side by side observation of live activities
Training recording to be done by leveraging collaboration tools like MS Teams
Capture tribal knowledge
SOP’s to be created/validated (step by step) using industry leading digital capture tools
Hands on/ practice/ simulations
Activities to be completed by EXL team under complete SME supervision (Training / Simulation environment created by EXL during “Show me” phase)
Prior period re-performance to be done where activities can’t be done for current period
SOP’s to be validated step by step & any missing steps to be updated
Performance/Documentation - Review
Review the work done by EXL team and provide feedback
Review & approve SOPs updated by EXL team
Guide on best practices and exception scenarios for timely completion of tasks
KT Certification
Conduct online weekly assessments of the KT team, simpler teach back sessions initially to more intensive activity performance / re-performance reviews
Prepare me
Tell me
Show me
Let me
Help me
Assess me
Knowledge Transfer

## Slide 22
EXL KT Governance Team – Responsibilities
Role | Responsibilities
KT Lead | Schedule meetings and block calendars Ensure all KT invites are sent in advance Ensure all EXL team members are logged on the KT sessions atleast 15 mins in advance Supervise the trainings of the processes aligned to them Provide the daily status of KT progress, update the query and issue logs Participate in daily KT / Supervised Production debrief call Lead daily team huddles (ensure appropriate knowledge retention) Check the SOP status with the team
KT SME | Additional support aligned during KT Will fill the business/process gaps of daily KT Will participate in all trainings
Overall Ops lead (Susan Paul – General Ledger Shibu Scariah – AP& TE) | Overall operations governance First point of contact for BSWH Process leads Part of all weekly / toll gate calls Resolve all open issues Drive the weekly status update calls with the BSWH process owners along with transition manager Participate in most daily calls
Transition Manager | Overall transition governance Part of all daily / weekly calls / toll gate calls Drive all tollgate calls Upload daily and weekly KT status playbook in MS Teams before the call 1st point of contact for any issues / concerns

## Slide 23
General Ledger KT Team – 3 in a BOX APPROACH
SL.No | Process | Sub – Process | KT SME | KT Lead | Transition Manager | Additional Support
1 | General Ledger | DFW Hospitals + FA | Sojan Mathew Wilson Devassy Lal Paul Shinu Shajee | Martin Varghese Selvam Pandiyan For Escalations:- Sajith Paul | Shagun John | 
2 |  | CTX Hospitals & Clinics + FA | Rajesh Ramaswamy Vishal Romy Linu Gopal | Eldho George Imthias Ameer For Escalations:- Sivaprasad Sreenivasan |  | 
3 |  |  |  |  |  | 
 |  | Leases | Lathikesh Kesavadas | Sivaprasad Sreenivasan |  | 
4 |  |  |  |  |  | 
 |  | Health Texas Clinics + FA | Abey George Ujjal Pankajakshan | Manu Manuel For Escalations:- Sivaprasad Sreenivasan |  | 
5 |  | Corporate Services, Other Operations & Foundation + FA | Arun Prakasan Deepak Sajeev | TBD |  | 

## Slide 24
AP&TE– 3 in a BOX APPROACH
SL.No | Process | Sub – Process | KT SME | KT Lead | Transition Manager | Additional Support
1 | AP & T&E | AP Strategy. Policy Set up & Acquisitions and Divestitures |  |  | Shagun John | 
2 |  | Vendor Set up |  | Fiona Joan Pereira |  | 
3 |  |  |  |  |  | 
 |  | Scanning |  | Vidya Kumble |  | 
4 |  |  |  |  |  | 
 |  | PO Invoice processing | Raghy Ravindran Lakshmi C M Chandrababu Ravi | Molbin George |  | 
5 |  | Non PO Invoice processing | Fifi P Cheeku Sanju Jacob | Molbin George |  | 
6 |  | Summary Bills | Nithin Raj | Vidya Kumble |  | 
7 |  | Patient Refunds | Saneersha B | Fiona Joan Pereira |  | 
8 |  | T&E Expense Process/Audit | Ashwin Narayan | Molbin George |  | 
9 |  | Disbursements | Saneersha B | Fiona Joan Pereira |  | 
10 |  | Customer Support | Roselin George Shinto Varghese Roshan Vadukoot | Febin K Abdulsalim |  | 
11 |  | Reporting and Analysis | Rashmita Ranjan Joji P S | Kiran Joy |  | 
12 |  | Accounting | Dipu P | Vidya Kumble |  | 
13 |  |  |  |  |  | 
 |  | Unclaimed Property |  | Molbin George |  | 

## Slide 25
Certification Process
Assessment and Certification Approach | 
Certification Approach | Option1 :- Assessment Time will be blocked in calendar in advance BSWH process owners/trainers will conduct an objective assessment every week based on the topics covered till that period The assessment will be uploaded on MS Team by BSWH trainers/process owners EXL associates will perform the test real time under supervision BSWH trainers/process owners to evaluate the assessment and share scores next day Feedback will be provided to individual resources by EXL team supervisor Option 2:-Teach Back Time will be blocked in calendar in advance During Teach Back assessment, BSWH trainers/process owner will ask 2-3 questions from each of EXL resources to gauge the knowledge acquired Questions will be based on the topics that that would be covered till date BSWH trainers/process owners to share feedback on a scorecard with EXL team supervisor and transition manager, who discusses the feedback with the resources Teach back assessment will be conducted every alternate week for processes in knowledge transfer stage Option 3:- Reverse Shadow It is process during KT, when EXL team members will perform the task from their systems and BSWH team will shadow During processing, real time feedback will be provided for all resources. EXL team supervisor will collect scores and share
Passing score > 80%, assessment approach to be finalized during KT basis nature and frequency of the activities

## Slide 26
Teach back Scorecard Format for option 2

## Slide 27
Status on BSWH Compliance Trainings
Trainings | AP&TE (Total staff: 50) | General Ledger (Total staff:34)
Baylor Scott & White Health Code of Conduct 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 10 users have completed their training, pending to be completed by 10/23 EOD
Making the Right Choice: Compliance Education 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 11 users have completed their training, pending to be completed by 10/23 EOD
HIPAA Training for Current Staff with Incidental Access to PHI 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 11 users have completed their training, pending to be completed by 10/23 EOD
Payment Card Industry Awareness Training for Managers 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 11 users have completed their training, pending to be completed by 10/23 EOD
Confidentiality and Security Agreement 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 11 users have completed their training, pending to be completed by 10/23 EOD
Safety in the Workplace Annual 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 30 users have completed their training, pending to be completed by 10/23 EOD
Introduction to Infection Prevention and Control for Non-Patient Facing Staff 2020 | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 30 users have completed their training, pending to be completed by 10/23 EOD
Boot Camp Finance Intro | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 30 users have completed their training, pending to be completed by 10/23 EOD
Boot Camp Finance Reports – The Bigger Picture | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 30 users have completed their training, pending to be completed by 10/23 EOD
Boot Camp Labor Management | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 30 users have completed their training, pending to be completed by 10/23 EOD
BSWH Work Safe Toolkit for Re-entry | - 34 users have completed their training, pending to be completed by 10/23 EOD | - 30 users have completed their training, pending to be completed by 10/23 EOD

## Slide 28
Proposed – Interim Technology solution architecture
Note: The above network schematic is a broad view of the proposed solution and does not depict the exact placement of the equipment.
  Network & Telecom
  Telecom connectivity over EXL’s Enterprise Internet between BSWH’s DC & EXL Delivery location for the in-scope data access
  WFO (Work From Office) Network:
Logically segregated, secured & resilient network with dedicated VLAN’s on multi-tier architecture
  WFH (Work From Home) Network:
    Global Protect VPN client on EXL Laptops to connect to EXL network and leverage proposed Internet connectivity to connect to BSWH's VDI (Citrix etc.)
    Disabled split-tunneling on endpoints to mandatorily route all traffic via EXL Corporate Network
  Systems & Applications
  WFO (Work From Office):
    Hardened Endpoints - Disabling local drive storage, screen shot, right click, Copy-paste feature, no internet access or restricted only for Client approved sites
    Enabled with Antivirus, Security Patch Mgmt. & DLP
  WFH (Work From Home):
    Hardened & encrypted Laptops – Disabled similar to WFO hardening
    DLP, AV, Encryption, URL filtering, Malware protection
    Agent Productivity Monitoring (AMMO), Performance dashboards
Technology Service Delivery (Applicable for both WFO and WFH)
    ITIL based Service Mgmt. Processes & Tools for Tech. Service Delivery & IT Governance
    24x7 Servicedesk; 24x7 Network Operations Center (NOC) and Security Operations Center (SOC)
    Information Security (Applicable for both WFO and WFH)
    EXL’s ISO 27001 ISMS framework with best in class InfoSec & Privacy controls
    EXL’s hardened perimeter security (NextGen FW, IPS & Anti-APT), Websense, DLP, NAC & SIEM
Connectivity Schematic
EXL’s Technology Solution provides a robust infrastructure covering all aspects including the split operations between WFO (Work From Office) and WFH (Work From Home), through a well established methodology and governance model
Technology Solution Overview

## Slide 29
Hybrid OPERATING MODEL: enhanced Information Security controls
System/Endpoint Security Controls:
    Data Loss Protection (DLP) solution
    McAfee EPO and McAfee Virus Scan enterprise solution for end point security
    Regular/emergency security patching & endpoint Encryption (disk & boot layer)
    Anti – APT (Endpoint Detect and Response), URL filtering & Malware protection solution installed on the endpoints
    Standard endpoint hardening practices to disable USBs, CDs, printing, right click feature (cut & paste), print screen, local storage and no Internet access or restricted access to client mandated sites only etc.
  Access to the in-scope applications through Client provisioned VDI/Citrix environment only
  Systems log using Two Factor authentication, viz. Computer Certificate level authorizing only EXL CORP domain active members and EXL’s Active Directory authentication
  Network level Controls:
  All endpoints use secure Global Protect VPN solution to connect to EXL corporate network using encrypted IPsec tunnel
  Internet access from EXL provided laptop systems is governed by corporate internet policy that is limited and recorded
  All user traffic traverses via EXL’s NextGen Palo Alto Firewalls
  Anti – APT solution implemented on the Network Layer
  Split-tunneling on user endpoints is disabled to mandatorily route all user traffic via secure EXL Corporate Network
  Network Access Control (NAC) solution is enabled for control and validation of the end point posture
  People & Policies:
  “Non Disclosure & Confidentiality Agreements” are signed by all WAH agents precisely covering clauses and associated disciplinary actions
  Standard and role based awareness trainings & mandatory tests
  Information Data Security & Privacy: Do's and Don’ts
  Information Security guidelines (covering laptop usage , Access control, Internet access, email access, password, clean desk, etc.)
EXL has implemented various safeguards & controls from Information security and Data privacy standpoint