## Implementation Plan
|  | Complete |  |  | WU/Convera
|  | On Schedule |  |  | Convera
Implementation Plan |  | At Risk |  |  | WU Activities
Delayed
Key tasks
WU - Accounts Payable |  | Not Due |  |  | Milestone
[5 empty] | Tollgate |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  |  | 2019-05-18
Task ID | Activities | Status | Duration (Days) | Planned Start Date | Planned End Date | Responsibility | time axis 2021-12-06 to 2022-10-31
1 | WU AP TRANSITION SUPPORT PLAN |  | 203 | 2021-12-06 | 2022-09-14
1.1 | PROGRAM LEVEL ACTIVITIES |  |  | 2021-12-06 | 2022-01-06
1.1 | Business Aware decision | Complete | 1 | 2021-12-06 | 2021-12-06 | WU/Convera | bar: 2021-12-06
1.2 | Project team to be identified | Complete | 1 | 2022-01-03 | 2022-01-03 | WU | bar: 2022-01-03
1.3 | Kick off meeting | Complete | 1 | 2022-01-06 | 2022-01-06 | WU | bar: 2022-01-03
2.1 | TRANSITION PLANNING & IT SET UP |  |  | 2021-12-06 | 2022-02-28
2.1 | Technology and Connectivity | Complete | 26 | 2021-12-06 | 2022-01-10 | WU | bar: 2021-12-06 to 2022-01-10
2.1.1 | User ID creation & testing | Complete | 7 | 2021-12-31 | 2022-01-10 | WU | bar: 2021-12-27 to 2022-01-10
2.1.2 | Enable currencies in global pay | Complete | 2 | 2022-01-10 | 2022-01-11 | WU | bar: 2022-01-10
2.1.3 | Test the payments, if the currencies are added | Complete | 1 | 2022-01-12 | 2022-01-12 | WU | bar: 2022-01-10
2.2 | VDI Connectivity for Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | Convera | bar: 2022-01-10 to 2022-01-17
2.2.1 | Move ERP to Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera
2.2.2 | All applications readiness to be confirmed in Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera
2.2.3 | Access to be provided in Convera environment | On Schedule | 28 | 2022-01-12 | 2022-02-20 | WU/ Convera
2.3 | Programming complete for Concur uploads | Complete | 16 | 2022-01-10 | 2022-01-31 | WU | bar: 2022-01-10 to 2022-01-31
2.3.1 | Creating Convera upload file according to WUBS Convera convention by business | Complete | 36 | 2022-01-10 | 2022-02-28 | WU | bar: 2022-01-10 to 2022-02-28
2.3.2 | Access to WIN SCP | Complete | 10 | 2022-01-10 | 2022-01-21 | WU | bar: 2022-01-10 to 2022-01-17
2.3.3 | Test WIN SCP | On Schedule | 34 | 2022-01-10 | 2022-02-24 | WU | bar: 2022-01-10 to 2022-02-14
2.4 | Convera Concur instance live | On Schedule | 31 | 2022-01-14 | 2022-02-25 | Convera
2.4.1 | Onboard EXL / WU in Convera Concur in new instance | On Schedule | 35 | 2022-01-10 | 2022-02-25 | Convera
2.4.2 | Convera Concur feed into WD | On Schedule | 35 | 2022-01-10 | 2022-02-25 | WU
2.4.3 | Creating Convera upload file according to WUBS Convera Concur convention by business | Complete | 35 | 2022-01-10 | 2022-02-25 | WU
2.5 | Communication regarding AP uploads | On Schedule | 36 | 2022-01-10 | 2022-02-28 | Convera | bar: 2022-01-10 to 2022-02-28
2.5.1 | Upload agreements in accordance with Convera | On Schedule | 36 | 2022-01-10 | 2022-02-28 | Convera | bar: 2022-01-10 to 2022-02-28
2.5.2 | Design internal audit requirement plan | On Schedule | 34 | 2022-01-10 | 2022-02-24 | Convera
2.6 | Designate approved invoice & vendor email boxes | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.6.1 | Threshold limit based on designation | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.6.2 | Approval matrix for PO invoices | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.6.3 | Approval matrix for Non PO invoices | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.6.4 | Automatic work flow approval to be initiated based on desgination | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.6.5 | Communication to be sent to WU procurement team to stop adding PO in WU environment | On Schedule | 14 | 2022-02-07 | 2022-02-24 | WU | bar: 2022-02-07 to 2022-02-21
2.6.6 | Remove WUBS procurement access for WU employees | On Schedule | 9 | 2022-02-14 | 2022-02-24 | WU | bar: 2022-02-07 to 2022-02-21
2.7 | Banking info for new entities in Convera AP | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.7.1 | Costa Rica : Create a new bank account | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.7.2 | Canada :Create a new bank account | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.7.3 | India : Create a new bank account | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.7.4 | Lithuania : Make sure the bank account is operational | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.7.5 | Switzerland : Existing account available to be confirmed | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.7.6 | USA: Existing account available to be confirmed | On Schedule | 33 | 2022-01-12 | 2022-02-25 | Convera
2.8 | Communication regarding vendor invoicing to Convera | On Schedule | 30 | 2022-01-14 | 2022-02-24 | Convera
2.8.1 | Identify Convera personnel for real estate | On Schedule | 30 | 2022-01-14 | 2022-02-24 | Convera
2.9 | Status of Convera iProcure | On Schedule | 30 | 2022-01-14 | 2022-02-24 | Convera
2.9.1 | Interim process for WUBS PO intake | On Schedule | 30 | 2022-01-14 | 2022-02-24 | Convera
2.9.2 | PO accrual process | On Schedule | 30 | 2022-01-14 | 2022-02-24 | WU
2.9.3 | Interim process for WUBS PO update | On Schedule | 34 | 2022-01-10 | 2022-02-24 | WU
2.9.4 | Manual tracking of PO details | On Schedule | 34 | 2022-01-10 | 2022-02-24 | WU
2.9.5 | Retrive the category segments for PO | On Schedule | 34 | 2022-01-10 | 2022-02-24 | Convera
3 | Convera AP feed from Work Day (WD) | On Schedule | 31 | 2022-01-14 | 2022-02-25 | Convera
3.1 | Convera Concur feed to Work Day (WD) | On Schedule | 31 | 2022-01-14 | 2022-02-25 | Convera
3.2 | Vendor management | On Schedule | 22 | 2022-01-27 | 2022-02-25 | Convera
3.2.1 | Vendor risk assessment | On Schedule | 22 | 2022-01-27 | 2022-02-25 | Convera | bar: 2022-01-24 to 2022-02-21
3.2.2 | OFAC check | On Schedule | 22 | 2022-01-27 | 2022-02-25 | Convera | bar: 2022-01-24 to 2022-02-21
3.2.3 | Call back to the vendor for bank details confirmation | On Schedule | 22 | 2022-01-27 | 2022-02-25 | Convera | bar: 2022-01-24 to 2022-02-21
4 | TRANSITION EXECUTION |  |  | 2022-02-21 | 2022-02-24
4.1 | Process Documentation, review & Sign off | Not Due | 4 | 2022-02-21 | 2022-02-24 | WU | bar: 2022-02-21
4.2 | Operations Set Up - Quality process, SLA trackers | Not Due | TBD | TBD | TBD | Convera
5 | PARALLEL RUN EXECUTION |  |  | 2022-09-01 | 2022-09-05
5.1 | Go live | Not Due | TBD | TBD | TBD | WU
5.2 | Exit of TSA | Not Due | 3 | 2022-09-01 | 2022-09-05 | bar: 2022-09-05
5.2.1 | Tollgate 1: Exit of TSA | Not Due | 3 | 2022-09-01 | 2022-09-05 | WU | 2022-09-05: WU; 2022-09-12: Exit of TSA
6 | STABLISATION COMMENCEMENT |  |  | 2022-09-12 | 2022-09-12
6.1 | Hand Over to Operations | Not Due | 3 | 2022-09-12 | 2022-09-14 | WU | bar: 2022-09-12
6.1.1 | Tollgate 2: Handover to operations | Not Due | 3 | 2022-09-12 | 2022-09-14 | WU | 2022-09-19: Handover to Operations
Formulas:
WU Activities = MAX([WU Activities, row below]:G71)
TBD = MIN([TBD, row below]:F69)
TBD = NETWORKDAYS([TBD],[WU Activities])
T
We are here
T1
Implementation Plan
T2

## Action Log
Action Log
# | Actions | Responsible | Target Completion | Impact | Status | Update / Comments (Month / Date)
1 | Convera Concur instance live Onboard EXL / WU in Convera Concur in new instance Convera Concur feed from WD | David_Convera | 2022-02-25 | High | On Schedule | a). The file submitted will be processed by AP team through AP TSA period (all other invoices are submitted from specified Convera individuals). b). Convera to request access file from Rich for assisting with this submission (WU to align internally to ensure no proprietary information is provided). Action item: David Ingham to determine how to they will provide the file for T&E to be paid via the AP TSA process (pre and post set up of Convera Concur instance).
2 | Communication regarding AP uploads, approvals & process flow Upload agreements in accordance with Convera | Andrey_Convera | 2022-02-28 | High | On Schedule | a). This team will work together to figure out which upload files will be provided by WU or Convera after close for the AP TSA. Cassandra to create a matrix with details regarding the current upload files and provide to this team. b). WU will need to determine how to unwind the WUBS upload files process. Action item 1: Stuart Burwood to create upload files for necessary vendors that will be submitted to EXL for processing under the AP TSA. Action item 2: Cassandra to provide matrix of upload files to team with updates regarding WU and Convera actions.
3 | Interim process for WUBS PO update | Andrey_Convera | 2022-02-18 | High | Completed | a). POs will be cut off and closed within the WU system as of 25-Mar. b). WU will provide a listing of the open POs as of that date for Convera to manually track on their side. EXL will get the invoices preapproved with GL codes(all details required to process the invoice and paid) | to be closed?
3 | AP Invoices | David_Convera | 2022-02-18 | High | On Schedule | Action item: David Ingham to provide list of Convera individuals who can submit AP files for payment (from a WU perspective, these invoices have been approved to be paid).
4 | Releasing of funds from bank account | Stuart_Convera/ Cassie_WU | 2022-01-27 | High | On Schedule | Action item: Funding requirement for Costa Rica and India payments –Cassandra to discuss with Chad
5 | Design the approval matrix & Need designated mail boxes | Stuart_Convera | 2022-02-25 | High | On Schedule | There are few individuals who have been identified from Convera who will be submitting invoices. We can proceed to make payment. Action item 1 : Designate an email box for sending approved invoices to WU : David \ Andrey Action item 2 : Send sample approved invoices to WU for testing: David / Andrey Action item 3 : Designate email box for sending approved vendor management requests: David / Andrey Action item 4 : Sent sample request forms for testing: David / Andrey
6 | Vendor management - Vendor risk assessment | Stuart_Convera | 2022-02-25 | Medium | On Schedule | Need to identify who is responsible for this task
7 | OFAC check | Stuart_Convera | 2022-02-25 | Medium | On Schedule | Need to identify whether this task needs to be continued
8 | Call back to the vendor for bank details confirmation | Stuart_Convera | 2022-02-25 | Medium | On Schedule | Need to identify a designated person in Convera to call back the vendor and confirm the bank account in vendor master
9 | Test WIN SCP | IT_WU | 2022-02-14 | Low | On Schedule | Once all access are received then testing to done as per Jally on weekly call dated 20-Jan. Still issues faced support being taken up with WU IT team, status as on 31-Jan.
10 | Provide high level | WU / EXL | 2022-02-25 | High | On Schedule | Action item: Prepare high level process flow for invoice processing and vendor creation and share it with Convera : WU / EXL
11 | Daily meeting (30minutes) to be set up for first two weeks of TSA | EXL | 2022-02-25 | High | On Schedule | Daily meeting (30minutes) to be set up for first two weeks of TSA between Convera, EXL & WU
| Performance testing on ERP | WU | 2022-01-09 |  | Completed | >>Performance testing completed.
| Test the payments, if the currencies are added | WU | 2022-01-17 |  | Completed | >>Testing could not be completed on 12-Jan. Retesting to be done as per Jally based on discussions on weekly call dated 13-Jan. >>The testing is completed & we were able to release the payment for multiple currencies, update as on 17-Jan, hence marking this action as complete.
| Programming complete for Concur uploads | Rich_WU | 2022-01-21 |  | Completed | >>Files are to be received on 13-Jan as per Rich based on discussions from weekly call dated 13-Jan. >>Files went out last week.
| Access to WIN SCP | IT_WU | 2022-01-21 |  | Completed | >>Access to WIN SCP is still pending to be recieved for team members as on 17-Jan. Access to inbound folder is not received.
| Creating Convera upload file according to WUBS Convera Concur convention by business | Rich_WU | 2022-01-21 |  | Completed
| Creating Convera upload file according to WUBS Convera Concur convention by business | Rich_WU | 2022-01-21 |  | Completed

## Application Status
|  | Last updated on 17-Jan IST 10:00 AM |  |  |  |  | Legend | Received | 100 | Pending | 25 | In-Progress | 75 | NA | 0
[5 empty] | Total Count | 10 | 40 | 40 | 40 | 40 | 35 | 30 | 27 | 8 | 35 | 40 | 27 | 27 | 25 | 35 | 6 | 32 | 23 | 40 | 37 | 23 | 8 | 8 | 40 | 8
|  | Updated by | Santosh Kumar |  | % Completion | 90% | 100% | 100% | 100% | 2.5% | 5.714% | 0% | 0% | 12.5% | 5.714% | 5% | 0% | 0% | -4% | 0% | 0% | -3.125% | -4.348% | 77.5% | 72.97% | 8.696% | 87.5% | 37.5% | 5% | 12.5%
[5 empty] | Pending Count | 1 | 0 | 0 | 0 | 39 | 33 | 30 | 27 | 7 | 33 | 38 | 27 | 27 | 26 | 35 | 6 | 33 | 24 | 9 | 10 | 21 | 1 | 5 | 38 | 7
|  | Resource Name & Role |  |  |  |  | Application Access Provisioning
|  | Name | SOW Job Title | Function Area | Location | WFH Capable/Tested | OKTA_ID | WU_Email ID | Oracle - Production | Concur | Noetix | Invoice Upload access | Workday | iProcurement | Shared Folder | Shared email box's | Taxport | WU Global Payables Supplier Maintenance | Payment Bank Accesses | Printer Access | WU Global Pay | Bank Of America | Citi Bank | Payment CAD-USD | Other Websites for Convera | Microsoft Office Application's | Snipping Tool | Reflection SFTP tool- WIN SCP | Box locator application | VDI Access in Convera
| 1 | Helan V A | Assistant Manager | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 2 | Thameem Meenatharakal K | Senior Associate | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 3 | Neethu Thomson | Senior Associate | Accounts Payable | Kochi | 100 | 100 | 100 | 100 | 25 | 100 | 75 | 0 | 25 | 100 | 100 | TBD | TBD | TBD | 75 | TBD | TBD | TBD | 75 | TBD | 100 | 100 | 75 | 100 | 75
| 4 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 5 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 100 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 6 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 5
| 7 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 0
| 8 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 9 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 10 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 11 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 12 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 13 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 75 | 0
100 | 14 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 15 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 16 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 17 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 18 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 19 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 75 | 0 | 0 | 0 | 75 | 75
| 20 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 21 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 22 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 23 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 0 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 0 | 0 | 0 | 75 | 75
| 24 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
| 25 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
| 26 |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 100 | 75 | 0
| 27 |  |  |  |  | 75 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 75 | 0 | 100 | 75 | 75 | 0
| 28 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 75 | 75 | 0
| 29 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 75 | 75 | 0 | 100 | 75 | 75 | 0
| 30 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 75 | 75 | 0 | 75 | 100 | 75 | 0
| 31 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 32 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 33 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 34 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 35 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0
| 36 |  |  |  |  | 100 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 0 | 100 | 75 | 0 | 0 | 0 | 75 | 0
| 37 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 38 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 39 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 75 | 0
| 40 |  |  |  |  | 0 | 100 | 100 | 100 | 75 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 75 | 0 | 75 | 75 | 75 | 100 | 100 | 0 | 0 | 0 | 75 | 0
|  | Susan Paul | AVP | Service Delivery Lead | LAROC |  | 100 | 100 | 100 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 0 | 75 | 75 | 100 | 100 | 75 | 0 | 0 | 75 | 0

## Risk Log
Risk Log
Sl NO | Risk Category | Risk Description | Effect of Risk | Impact | Action to Mitigate | Risk Owner | Status | Target Resolution Date | Status Update
1 | Process | Vendor master creation of new entities | >>No information on volumes from new entities >>Can impact payments to the vendors | High | Vendor details for new entities is required | Andrey_Convera | Open | 2022-02-15 | >>Complete vendor list & banking details are required as per Jally based on discussions in weekly connect dated 13-Feb >>Convera support is required on this topic.
2 | Process | Approver matrix - Not received the approver list | >>Invoice will not be posted & settled in ERP | Medium | Convera to provide the details | Andrey_Convera | Open | 2022-02-21 | >>Convera support is required on this topic.
3 | Process | Segregation of Duties (SOD) | >>Team will only be able to process one functional area if SOD is applicable, Need additional resource in each functional area | Medium | As the team size is small, Segregation of duties might not be applicable at this stage but will be required at later stage | Andrey_Convera | Open | 2022-02-15 | >>Joe asked to check with Stuart for the status update on SoD as per weekly call dated 13-Jan.
4 | Process | Minimal information on volumes for new entities | >>If the volumes vary then there is possibility of backlogs | Medium | Team to review the volumes for next 2 months | Carey_WU | Open | 2022-02-10
5 | Process | Communication to vendors on WU-Convera separation | >>If the vendors are not informed then WU will continue to receive the invoices of Convera >>Payment will be delayed. | Low | Vendors to be informed about the change & request them to provide invoices to WUBS (Convera) shared mail box | Carey_WU / Andrey_Convera | Open | 2022-02-15 | >>Mass communication is not required to vendors as per Joe based on discussions on weekly connect dated 13-Jan.. >>Currently there is a vendor work stream that is worked upon with Convera. Carey informed that they have added an new inbox on weekly call dated 20-Jan.
6 | Process | Training on AP uploads to the requestor | >>If the requestor enters wrong GL code then system accepts the incorrect GL codes, hence it will impact the GL accounts. >>Upload file convention to be followed while submitting for processing | High | >>Is there any mechanism where system does not allow the incorrect GL codes, this needs to be confirmed >>Train the requestors & provide them with the correct GL codes information | Carey_WU | Closed | 2022-04-30 | >>Joe informed that this will remain between EXL & Convera as per discussions in weekly connect dated 13-Jan. >>This topic needs to be part of Implementation plan as per Joe as per discussions in weekly connect dated 13-Jan. >>This risk is closed post discussion with Jally & Helan on 10th Feb
7 | Process | Duplicate checks are not performed | >>Chances of double payment from WU & Convera | High | Implement EXL’s fraudulent check tool | Andrey_Convera | Open | 2022-02-28 | >>Needs to be confirmed by 28-Feb whether duplicate checks are required or not
8 | Process | ACH payment method and check payment method : Positive pay file transfer to bank is not developed by IT in Convera system | >>Payment will not be not be settled for ACH & for bank will not be aware of cheques being issued | High | Technology team has to provide these details | IT | Closed | 2022-01-13 | >>As per discussions by Joe on weekly call dated 13-Jan, this risk item is closed.
9 | Technology | Access to bank information | >> Not be able to check which payment has been settled and which payment has been returned | Medium | >>Need to check with treasury to provide proof of payment for payment queries | Andrey_Convera | Open | 2022-02-15 | >>As per the update from Jally on weekly connect dated 13-Jan, there is a back-up plan in place but EXL does not have access to bank details.
10 | Technology | IT communcation plan does not exist | >>Team will not be able to contact the technology related or IT related issues | High | Create an IT communication plan | WU / IT | Closed | 2022-01-14 | >>To check with Brian as per Joe based on discussions in weekly call dated 13-Jan. >>Brian has provided these details hence marking it as complete.
11 | Technology | Concur login | >>If Convera employees have access to WU Okta after close one | Low | Link to a website or log in page, password to be provided | Rich_WU / IT | Open | 2022-02-21
12 | Process | Final reconcillation of credit card transactions | >>Complete reconcillation is not possible, WU will have to handle this at a later stage | Medium | To monitor the unreconcilled expenses | Rich_WU | Open | 2022-03-15 | >> Currently the expense administration team will be monitoring this till the close of February as per weekly connect dated 13-Jan.
13 | Technology | VDI access within the WU environment | >>Not able to review the accounts or invoices | High | VDI access to continue in WU environment during the TSA period | WU / Convera IT | Closed | 2022-02-28 | >>When VDI access moves to Convera environment, a VDI Convera access should be there. Needs to be confirmed with Brian. >>Jally informed that an MSA and SOW should be incorporated between Convera & EXL for IT team to provide access >>Has been closed post discussion with Helan & Jally
14 | People | No buffer when it comes to count of resources | >>There are only 3 resources for this transition, if there is any attrition then it will impact the production. >>Transition could be delayed if there is attrition | Low | Currently assigned experienced resources hence buffer might not be required | Andrey_Convera | Open | 2022-02-10
15 | People | Shared resource for vendor management between WU & Convera | >>The resource has to work on both , we will not be able to use this resource in convera environment | High | Additional resource required for vendor management | Carey_WU / Andrey_Convera | Open | 2022-02-28
16 | Technology | Single License | Only one resource has access to Vendor master | High | Additional access is required as there is a possibility that one resource can go on leave | Andrey_Convera | Open | 2022-02-15 | >>Convera support is required on this topic.
17 | Process | Positive pay, OCP payment & BAI process | Unable to perform these activities without bank access. | Low | >>Bank access is required | Carey_WU | Open | 2022-02-25 | >>Need bank access as per internal team