## Home (hidden)
Prudential Medical Underwriting Training to EXL Team
Knowledge Transfer Tracker
Issue Concerns
Systems Login
Attendance Tracker
Assessment - Report Card
Summary
Schedule & Status

## KT Summary
Week Commencing | Training Type | RAG Status (Actual Vs Planned Training) | Training Issues | System Access Status | EXL Personnel Concerns | Look ahead for next week
7th Jun 2021 | Process Training - RSA Validation |  | None | Access being checked for each individual, some accesses are still pending | None
14th Jun 2021 | Process Training - Followup letters |  | None | Most of the accss issues have been resolved, only ERS access pending for one trainee | None
21st Jun 2021 | Process Training - Followup letters |  | None | Most of the accss issues have been resolved, only ERS access pending for one trainee | None
28th Jun 2021 | Nesting - Followup letters RSA Validation |  | None |  | None
5th Jul 2021 | Nesting - Followup letters |  | None |  | None
12th Jul 2021 | Process Training - APO |  | None |  | None
19th Jul 2021 | Process Training - APO |  | None |  | None
26th Jul 2021 | Lump Sum |  | None |  | None
2nd Aug 2021 | Lump Sum |  | None |  | None
9th Aug | Nesting - Lump Sum and APO |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None
|  |  | None |  | None

## KT Schedule & Status
Policy Review and Process Intervention
On Schedule
|  | Overall status |  |  | 1 day behind
>=2 day behind
Week 1 | Date |  |  | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11
| Time | Training | Agenda | Trainer: Emily Maple Topic: Introduction and Systems Overview. RSA Validation | Trainer: Emily Maple and Lisa Dugan Topic: RSA Validation | Trainer: Emily Maple and Lisa Dugan Topic: RSA Validation | Trainer: Emily Maple and Lisa Dugan Topic: RSA Validation | Trainer: Emily Maple and Lisa Dugan Topic: RSA Validation
| 8 AM to 4 PM EST | Process Training | Agenda | Introduction Icebreaker System Access Check Systems Navigation and Overview Overview of RSA Validation | RSA Validation Procedures Internal team huddle Debrief / Refresher | VPAS RSA Validation Process and Procedure Internal team huddle Debrief / Refresher | Introduction of LifeCad RSA Validation practice LifeCad RSA Validation Practice Internal team huddle Debrief / Refresher | Introduction of FAST RSA Validation Practice VPAS/LifeCad/ FAST RSA Validation Practice Internal team huddle, Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 2 | Date |  |  | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18
| Time | Training | Agenda | Trainer: Emily Maple Topic: Annuities 101 and Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters
| 8 AM to 4 PM EST | Process Training | Agenda | Annuities 101 Introduction to follow up letters, Purpose and objectives Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Shadowing) Internal team huddle Debrief / Refresher | VPAS follow up letter practice (Solo) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Wwek 3 | Date |  |  | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25
| Time | Training | Agenda | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters
| 8 AM to 4 PM EST | Process Training | Agenda | RPA BOT procedures RPA BOT procedures practice Internal team huddle Debrief / Refresher | Fast follow up letters Internal team huddle Debrief / Refresher | Lifecad follow up letters (Shadowing) Lifecad follow up letters (Solo) Internal team huddle Debrief / Refresher | Lifecad follow up letters (Solo) Internal team huddle Debrief / Refresher | VPAS/FAST/Lifecad follow up letters (Solo) RSA Validation processing Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 4 | Date |  |  | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02
| Time | Training | Agenda | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters | Trainer: Emily Maple Topic: Follow Up Letters
| 8 AM to 4 PM EST | Process Training | Agenda | Followup Letter (Solo) Internal team huddle Debrief / Refresher | Followup Letter (Solo) Internal team huddle Debrief / Refresher | Followup Letter (Solo) Internal team huddle Debrief / Refresher | Followup Letter (Solo) Internal team huddle Debrief / Refresher | Followup Letter (Solo) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 5 | Date |  |  | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09
| Time | Training | Agenda | Trainer: Tracy and David Topic: Follow Up Letters | Trainer: Tracy and David Topic: Follow Up Letters | Trainer: Emily Maple Topic: RSA Validation | Trainer: Emily Maple Topic: RSA Validation | Trainer: Emily Maple Topic: Follow Up Letters and RSA Validation
| 8 AM to 4 PM EST | Process Training | Agenda | Followup Letter (Solo) Internal team huddle Debrief / Refresher | Followup Letter (Solo) Internal team huddle Debrief / Refresher | RSA Validation (Solo) Internal team huddle Debrief / Refresher | RSA Validation (Solo) Internal team huddle Debrief / Refresher | Followup Letters and RSA Validation (Solo) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 6 | Date |  |  | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16
| Time | Training | Agenda | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO
| 8 AM to 4 PM EST | Process Training | Agenda | Introduction of APO process, purpose and objectives Internal team huddle Debrief / Refresher | APO processing/ (Shadowing) Internal team huddle Debrief / Refresher | APO processing / (Solo) Internal team huddle Debrief / Refresher | APO processing/(Solo) Internal team huddle Debrief / Refresher | APO processing/(Solo) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 7 | Date |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23
| Time | Training | Agenda | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO | Trainer: Emily Maple and Sabrina Topic: APO
| 8 AM to 4 PM EST | Process Training | Agenda | LifeCad APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | LifeCad APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | LifeCad APO Processing (Solo) AOS APO Processing (Shadowing) Follow Up Letters Processing Internal team huddle Debrief / Refresher | VPAS/FAST/LifeCad APO Processing (Solo) Follow Up Letters Processing Internal team huddle Debrief / Refresher | VPAS/FAST/LifeCad APO Processing (Solo) Follow Up Letters Processing Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 8 | Date |  |  | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30
| Time | Training | Agenda | Trainer: Tracy Bostic Topic: Lump Sum | Trainer: Tracy Bostic Topic: Lump Sum | Trainer: Tracy Bostic Topic: Lump Sum | Trainer: Tracy Bostic Topic: Lump Sum | Trainer: Tracy Bostic Topic: Lump Sum
| 8 AM to 4 PM EST | Process Training | Agenda | Overview of good order requirements and claims form Death Certificate and beneficiary types Internal team huddle Debrief / Refresher | Claims option and claims requirements BPC notes templates Internal team huddle Debrief / Refresher | Due proof review and moving funds DCI and BOT Internal team huddle Debrief / Refresher | Outstanding checks in pride, Lump sum to receiving companies, Concierge and Platinum VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | NIGO, procedures, estimation, Child Support database searches VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 9 | Date |  |  | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06
| Time | Training | Agenda | Trainer: Emily Maple Topic: Lump Sum | Trainer: Emily Maple Topic: Lump Sum | Trainer: Emily Maple Topic: Lump Sum | Trainer: Emily Maple Topic: Lump Sum | Trainer: Emily Maple Topic: Lump Sum
| 8 AM to 4 PM EST | Process Training | Agenda | Lump sum on BCO TDA, Roth, IRA, minor beneficiaries Internal team huddle Debrief / Refresher Custodian | Manual Checks, Reversals, AIT fixes VPAS Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | Introduction of Lifecad Lump sum Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | Lifecad Lump sum practice (Shadowing) Internal team huddle Debrief / Refresher | PIP Contracts Lifecad Lump sum pactice (Shadowing) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 10 | Date |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13
| Time | Training | Agenda | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO
| 8 AM to 4 PM EST | Process Training | Agenda | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 11 | Date |  |  | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20
| Time | Training | Agenda | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO | Trainer: Emily Maple Topic: Lump Sum and APO
| 8 AM to 4 PM EST | Process Training | Agenda | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher | APO/Lump sum practice(Solo) Internal team huddle Debrief / Refresher
SOP Link and navigation
Actual (RAG status)
Week 12 | Date |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 13 | Date |  |  | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 14 | Date |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 15 | Date |  |  | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 16 | Date |  |  | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 17 | Date |  |  | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 18 | Date |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda | Ramp in progress
SOP Link and navigation
Actual (RAG status)
Week 19 | Date |  |  | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda
SOP Link and navigation
Actual (RAG status)
Week 20 | Date |  |  | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda
SOP Link and navigation
Actual (RAG status)
Week 21 | Date |  |  | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda
SOP Link and navigation
Actual (RAG status)
Week 22 | Date |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda
SOP Link and navigation
Actual (RAG status)
Week 23 | Date |  |  | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda
SOP Link and navigation
Actual (RAG status)
Week 24 | Date |  |  | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19
| Time | Training | Agenda
| 8 AM to 4 PM EST | Process Training | Agenda
SOP Link and navigation
Actual (RAG status)
Formulas:
Trainer: Tracy Bostic Topic: Lump Sum = [Trainer: Tracy Bostic Topic: Lump Sum]+1

## ABS Ramp (hidden)
Annuities Bene Services
Production | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | Week of Aug 23rd | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | Week of Aug 30th | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | Week of Sep 6th | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | Week of Sep 13th | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | Week of Sep 20th | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Week of Sep 27th | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | Week of Oct 4th | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | Week of Oct 11th
Work Type 1 (14/hr) | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Work Type 2 (13/hr) | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Production Counts - Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | Week of Aug 23rd | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | Week of Aug 30th | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | Week of Sep 6th | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | Week of Sep 13th | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | Week of Sep 20th | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Week of Sep 27th | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | Week of Oct 4th | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | Week of Oct 11th
Total Cases Reviewed | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Total Transactions Reviewed | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Total Errors | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Quality %
Transactional Score |  | 189 | 91 | 157 | 139 | 576 | 72 | 143 | 147 | 224 | 304 | 890 | 119 | 112 | 47 | 155 | 87 | 520 | 99 | 172 | 277 | 274 | 271 | 1093 | 214 | 146 | 231 | 258 | 276 | 1125 | 390 | 377 | 474 |  |  | 1241 | [5 empty] | 0 | [5 empty] | 0
Transactional Errors |  | 9 | 4 | 1 | 1 | 15 | 1 | 7 | 4 | 6 | 3 | 21 | 0 | 1 | 3 | 1 | 0 | 5 | 1 | 3 | 9 | 4 | 6 | 23 | 7 | 1 | 4 | 8 | 24 | 44 | 19 | 12 | 18 |  |  | 49 | [5 empty] | 0 | [5 empty] | 0
Quality % |  | 95.24% | 95.6% | 99.36% | 99.28% | 97.4% | 98.61% | 95.1% | 97.28% | 97.32% | 99.01% | 97.64% | 100% | 99.11% | 93.62% | 99.35% | 100% | 99.04% | 98.99% | 98.26% | 96.75% | 98.54% | 97.79% | 97.9% | 96.73% | 99.32% | 98.27% | 96.9% | 91.3% | 96.09% | 95.13% | 96.82% | 96.2% |  |  | 96.05%
Target Quality % | 70% | 70% | 70% | 70% | 70% | 70% | 80% | 80% | 80% | 80% | 80% | 80% | 90% | 90% | 90% | 90% | 90% | 90% | 85% | 85% | 85% | 85% | 85% | 85% | 70% | 70% | 70% | 70% | 70% | 70% | 90% | 90% | 90% | 90% | 90% | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 98% | 98% | 98% | 98% | 98% | 98%
Forms | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | Week of Aug 23rd | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | Week of Aug 30th | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | Week of Sep 6th | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | Week of Sep 13th | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | Week of Sep 20th | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Week of Sep 27th | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | Week of Oct 4th | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | Week of Oct 11th
Effective Hours of Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Required Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prudential System Downtime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA Downtime | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Idle Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Training Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overtime Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjusted Required Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Productive
Target Productivity % | 70% | 70% | 70% | 70% | 70% | 70% | 80% | 80% | 80% | 80% | 80% | 80% | 50% | 50% | 50% | 50% | 50% | 50% | 70% | 70% | 70% | 70% | 70% | 70% | 50% | 50% | 50% | 50% | 50% | 50% | 80% | 80% | 80% | 80% | 80% | 80% | 90% | 90% | 90% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100%

## ABS-Ramp
Annuities Bene Services
Production | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | Week of Aug 23rd | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | Week of Aug 30th | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | Week of Sep 6th | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | Week of Sep 13th | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | Week of Sep 20th | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Week of Sep 27th | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | Week of Oct 4th | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | Week of Oct 11th | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | Week of Oct 18th | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | Week of Oct 25th | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | Week of Nov 1st | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | Week of Nov 8th | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | Week of Nov 15th | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | Week of Nov 22nd
Followup Letters | 45 | 54 | 14 | 22 | 24 | 159 | 36 | 23 | 26 | 38 | 36 | 159 | OFF | 43 | 45 | 44 | 47 | 179 | 50 | 80 | 44 | 6 | 25 | 205 | 23 | 18 | 6 | 5 |  | 52 | 55 | 55 | 2 | 41 | 38 | 191 |  | 40 |  |  |  | 40 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
RSA Validation | [5 empty] | 0 |  |  |  | 90 |  | 90 | OFF | 91 |  |  |  | 91 |  |  | 120 | 90 | 110 | 320 | 47 | 30 | 72 | 40 | 58 | 247 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
APO | 21 | 24 | 10 | 13 | 7 | 75 | 6 | 1 | 2 | 1 | 2 | 12 | OFF | 3 | 13 |  |  | 16 | 1 | 1 | 48 | 1 |  | 51 |  | 1 | 7 |  |  | 8 | 4 | 1 | 42 |  | 13 | 60 | 19
Lump Sum |  | 14 | 10 | 24 | 16 | 64 | 10 | 19 | 24 | 36 | 26 | 115 | OFF | 9 | 27 | 36 | 33 | 105 | 31 | 25 | 9 | 16 | 37 | 118 |  | 48 | 48 | 46 | 40 | 182 | 38 | 23 | 34 | 45 | 41 | 181 | 40 | 59
Production Counts - Total | 66 | 92 | 34 | 59 | 47 | 298 | 52 | 43 | 52 | 165 | 64 | 376 | 0 | 146 | 85 | 80 | 80 | 391 | 82 | 106 | 221 | 113 | 172 | 694 | 70 | 97 | 133 | 91 | 98 | 489 | 97 | 79 | 78 | 86 | 92 | 432 | 59 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Productivity (based on assigned volumes) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Target Productivity | 20% | 20% | 20% | 20% | 20% | 20% | 30% | 30% | 30% | 30% | 30% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 50% | 50% | 50% | 50% | 50% | 50% | 60% | 60% | 60% | 60% | 60% | 60% | 70% | 70% | 70% | 70% | 70% | 70% | 80% | 80% | 80% | 80% | 80% | 80% | 90% | 90% | 90% | 90% | 90% | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 98% | 98% | 98% | 98% | 98% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Quality | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | Week of Aug 23rd | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | Week of Aug 30th | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | Week of Sep 6th | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | Week of Sep 13th | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | Week of Sep 20th | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Week of Sep 27th | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | Week of Oct 4th | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | Week of Oct 11th | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | Week of Oct 18th | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | Week of Oct 25th | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | Week of Nov 1st | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | Week of Nov 8th | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | Week of Nov 15th | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | Week of Nov 22nd
Follow up - Cases Reviewed | [24 empty] | 21 | 4 | 3 | 3 | 51 | 82 | 60 | 43 | 2 | 37 | 22 | 164 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Follow up - Total Errors | [24 empty] | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 6 | 7 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Followup Quality % | [24 empty] | 95.24% | 100% | 100% | 100% | 98.04% | 97.56% | 98.33% | 100% | 100% | 100% | 72.73% | 95.73%
RSA - Cases Reviewed | [24 empty] | 49 | 76 | 87 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
RSA - Total Errors | [24 empty] | 3 | 1 | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
RSA Quality % | [24 empty] | 93.88% | 98.68% | 98.85% |  |  | 97.64%
APO - Cases Reviewed | [24 empty] | 7 | 3 | 12 | 25 | 5 | 52 | 5 | 0 | 36 | 19 | 19 | 79 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
APO - Total Errors | [24 empty] | 0 | 0 | 4 | 1 | 1 | 6 | 0 | 0 | 0 | 1 | 4 | 5 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
APO Quality % | [24 empty] | 100% | 100% | 66.67% | 96% | 80% | 88.46% | 100% |  | 100% | 94.74% | 78.95% | 93.67%
Lump Sum - Cases Reviewed | [24 empty] | 2 | 32 | 34 | 33 | 17 | 118 | 37 | 23 | 23 | 36 | 29 | 148 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Lump Sum - Total Errors | [24 empty] | 0 | 10 | 5 | 8 | 2 | 25 | 6 | 6 | 6 | 6 | 4 | 28 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Lump Sum Quality % | [24 empty] | 100% | 68.75% | 85.29% | 75.76% | 88.24% | 78.81% | 83.78% | 73.91% | 73.91% | 83.33% | 86.21% | 81.08%
Total Cases Reviewed | 66 | 53 | 34 | 56 | 46 | 255 | 53 | 56 | 65 | 124 | 125 | 423 | OFF | 91 | 60 | 68 | 65 | 284 | 74 | 65 | 82 | 92 | 155 | 468 | 76 | 115 | 136 | 61 | 73 | 461 | 102 | 66 | 61 | 92 | 70 | 391 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Total Errors | 5 | 2 | 2 | 7 | 8 | 24 | 11 | 9 | 5 | 6 | 4 | 35 | OFF | 0 | 2 | 10 | 3 | 15 | 9 | 6 | 3 | 10 | 17 | 45 | 4 | 11 | 10 | 9 | 4 | 38 | 7 | 6 | 6 | 7 | 14 | 40 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
Quality % | 92.42% | 96.23% | 94.12% | 87.5% | 82.61% | 90.59% | 79.25% | 83.93% | 92.31% | 95.16% | 96.8% | 91.73% | OFF | 100% | 96.67% | 85.29% | 95.38% | 94.72% | 87.84% | 90.77% | 96.34% | 89.13% | 89.03% | 90.38% | 94.74% | 90.43% | 92.65% | 85.25% | 94.52% | 91.76% | 93.14% | 90.91% | 90.16% | 92.39% | 80% | 89.77%
Target Quality % | 80% | 80% | 80% | 80% | 80% | 80% | 82% | 82% | 82% | 82% | 82% | 82% | 85% | 85% | 85% | 85% | 85% | 85% | 88% | 88% | 88% | 88% | 88% | 88% | 90% | 90% | 90% | 90% | 90% | 90% | 92% | 92% | 92% | 92% | 92% | 92% | 94% | 94% | 94% | 94% | 94% | 94% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 96% | 96% | 96% | 96% | 96% | 96% | 96% | 96% | 96% | 96% | 96% | 96% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 97%
Note on A8: Suhel Wasim: Based on daily volumes assigned by Prudential team

## Attendance Tracker
Process Training Attendance Tracker | [22 empty] | Legend
Attrite
Holiday
[23 empty] | P |  | Present
[23 empty] | L |  | Late
[23 empty] | A |  | Absent
Weekly Off
WEEK |  |  | Process Training Week 1 |  |  |  |  | Process Training - Week 2 |  |  |  |  | Process Training - Week 3 |  |  |  |  | Process Training - Week 4 |  |  |  |  | Process Training - Week 5 |  |  |  |  | Process Training - Week 6 |  |  |  |  | Process Training - Week 7 |  |  |  |  | Process Training - Week 8 |  |  |  |  | Process Training - Week 9 |  |  |  |  | Process Training - Week 10 |  |  |  |  | Process Training - Week 11 |  |  |  |  | Process Training - Week 12 |  |  |  |  | Process Training - Week 13 |  |  |  |  | Process Training - Week 14 |  |  |  |  | Process Training - Week 14 |  |  |  |  | Process Training - Week 15 |  |  |  |  | Process Training - Week 16 |  |  |  |  | Process Training - Week 16 |  |  |  |  | Process Training - Week 16 |  |  |  |  | Process Training - Week 17 |  |  |  |  | Process Training - Week 18 |  |  |  |  | Process Training - Week 19 |  |  |  |  | Process Training - Week 20 |  |  |  |  | Process Training - Week 21
S.NO. | Employee Code | Participants | time axis 2021-06-07 to 2021-11-19
 | time axis 2021-06-07 to 2021-11-19
ABS
1 | 162623 | Amit Kumar Rai | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday |  | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
2 | 162629 | Harsh Vardhan Shahi | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
3 | 162624 | Jyoti . | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
4 | 162626 | Kusum . | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
5 | 162628 | Naveen Kumar | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
6 | 162630 | Neelam Kumari | P | P | P | P | P | P | P | P | P | P | A | A | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
7 | 162631 | Neetu Gautam | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
8 | 162633 | Shristi Maheshwari | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
9 | 162625 | Shweta Singh | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
10 | 162627 | Gaurav Mishra | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
11 | 162632 | Yashika Gupta | P | P | P | A | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | A | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | A | P | P | P | P | P | A | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
12 | 162738 | Sheela Bagh | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
13 | 142990 | Trilok Sharma | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | A | A | A | A | A | A | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
14 | 136945 | Versha . | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
15 | 163556 | Aarjoo Ahmed Siddiqui | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
16 | 163700 | Gaurav Bhandari | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P
17 | 163377 | Pinki Kashyap | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | Holiday | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P | P

## Systems Login
N | Access Not Available
Y | Access Available
Y | Application installed but facing challenges
Process | Name of the associate | Role | User Name | User ID | LifeCAD | VPAS | BPC | Bronze | PIPS | PRIDE | Shared Drives / SharePoint | ERS | AOS | Secure Ability | MS Teams | Centralized Mailbox (MS Outlook) | MS Office | Adobe Acrobat | Lotus Notes / Email | Accurint | FAST
Annuities Bene Services | Amit Kumar Rai | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Harsh Vardhan Shahi | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Jyoti . | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Kusum . | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Naveen Kumar | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Neelam Kumari | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Neetu Gautam | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Shristi Maheshwari | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Shweta Singh | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Gaurav Mishra | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Yashika Gupta | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Sheela Bagh | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Trilok Sharma | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Versha . | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Aarjoo Ahmed Siddiqui | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Gaurav Bhandari | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y
| Pinki Kashyap | Associate |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Not checked | Not checked | Y | Y | Y | Y | Not checked | Y | Y

## KT Assessment - Report Card
Report Card
Policy Review
|  |  | Week 1 |  |  | Week 1 |  |  | Week 2 |  |  | Week 3
| Quiz # |  | Quiz 1 |  |  | Quiz 2 |  |  | Quiz 3 |  |  | Quiz 4 |  |  | Quiz 5
Name of the assessment
S.NO. | Process | Participants / Trainees | Total Qs: | 5 |  | Total Qs: | 5 |  | Total Qs: |  |  | Total Qs: |  |  | Total Qs:
|  |  | Rating | Retake (%) |  | Rating | Retake (%) |  | Rating | Retake (%) |  | Rating | Retake (%) |  | Rating | Retake (%)
|  |  |  | 1st | 2nd |  | 1st | 2nd |  | 1st | 2nd |  | 1st | 2nd |  | 1st | 2nd
1 |  | Amit Kumar Rai |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Harsh Vardhan Shahi |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Jyoti . |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Kusum . |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 80% | 100%
|  | Naveen Kumar |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Neelam Kumari |  | 100% |  |  | 100% |  |  | 80% | 100% |  | 100% |  |  | 80% | 100%
|  | Neetu Gautam |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Shristi Maheshwari |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Shweta Singh |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Gaurav Mishra |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%
|  | Yashika Gupta |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 70% | 100%
|  | Sheela Bagh |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 50% | 100%
|  | Trilok Sharma |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 80% | 100%
|  | Versha . |  | 100% |  |  | 100% |  |  | 80% | 100% |  | 100% |  |  | 100%
|  | Aarjoo Ahmed Siddiqui |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 60% | 100%
|  | Gaurav Bhandari |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 40% | 90%
|  | Pinki Kashyap |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 70% | 100%
| Policy Review | Total Class Size: | 17 |  |  | 17 |  |  | 17 |  |  | 17 |  |  | 17
|  | Trainee count with targets meet: | 17 |  |  | 17 |  |  | 17 |  |  | 17 |  |  | 17
|  | Total Class Average: | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100%

## Risks
Risk Description | [11 empty] | Risk Response Plan
Risk # | Date Identified | Risk Category | Sub - Category | Status | Cause | Risk | Impact | Action to Mitigate | Risk Owner | Target Resolution Date | Actual Resolution Date | Status Update
1 | 2021-08-20 | Ramp |  | Open | Unavailability of sufficient volume | EXL not able to meet expected production targets due to unavailability of sufficient volume | Medium | -Production targets to be adjusted in case of non-availability of sufficient volume - Actual volumesassigned will be considered as the target in case of lower volumes | EXL/ Prudential
2 | 2021-08-30 | Quality |  | Open | Lack of calibration exercise and certification guidelines | EXL Quality team not able to perform quality audits in steady state due to lack of calibration exercise and certification guidelines | Medium | - Calibration exercise to be conducted during initial ramp phase to onboard EXL QCA | EXL/ Prudential
3 | 2021-08-30 | Quality |  | Open | Calibration issues between Tech leads, Examiners, Trainer, and Quality Auditor | Variance and incorrect audits | Medium | -Weekly calibration meeting with all stakeholders to cover scenarios / issues during ramp period | EXL/ Prudential
4 | 2021-08-30 | Quality |  | Open | Quality performance issues due to lack of understanding on quality audit parameters | Variance and incorrect audits | High | -Separate training to be conducted on Quality audit sheet for underwriters to understand quality methodology and transactional / Gold Star errors | EXL/ Prudential
3 | 2021-03-01 | Hiring |  | Closed | Non vailability of resources | Delay in start of training | High | -EXL has already initiated shortlisting of candidates and keeping them on hold to reduce hiring time. Offer will be released post business go ahead. -EXL is also assessing possibility to seed resources within EXL with relevant experience | EXL | 2021-04-15 | 2021-05-01
4 | 2021-03-01 | Training |  | Closed | Lack of relevant experience | Extended Training time and longer learning curve due to lack of relevant experience | Medium | -Resource hired basis agreed skill set -Candidates went through assessment and interview process to ensure fitment to the process | EXL | 2021-04-15 | 2021-05-01
5 | 2021-03-01 | Training |  | Closed | Lack of training plan | Less impactful training due to lack of clear laid down training plan | High | -Prudential to create Training agenda which includes hourly schedule of training modules along with Assessments for knowledge check | Prudential | 2021-05-15 | 2021-05-15
6 | 2021-03-01 | Training |  | Closed | Prudential traininer non availability | Trainer not available during Training period due to various reasons | Medium | -Prudential identified Back up trainer to fill in for primary trainer and onboard Back up trainer on proposed plan | Prudential | 2021-04-15 | 2021-04-15
7 | 2021-03-01 | Technology |  | Closed | Non vailability of system access | Delay in KT due to unavailability of access to required systems or applications | High | -Prudential to procure VDI session licenses well in advance -During due diligence, Prudential and EXL finalized list of systems / applications required - EXL shared list of resources immediately after joining of the resources - Prudential Technology SPOC to help troubleshoot, if required | Prudential/ EXL | 2021-05-18 | 2021-06-14
8 | 2021-08-10 | Ramp |  | Closed | Movement of the trainer/SME to another department | Lack of support and risk of insufficient audits during ramp | High | - Backup trainer/ SME identifies and will be working along side the departing trainer to ensure consitency and a smooth handover | Prudential | 2021-08-20 | 2021-08-20
9
10
11
12
13
14
15
16
17
18
19

## Action
Log # | Activity | Action Item | Priority | Owner | Impact, if not completed | Comments | Date Identified | Target CompletionDate | Actual Completion Date
Open Action Items
1 | Quality Audits | EXL team to identify and Prudential to certify 2-3 team members on conducting audits for APO and RSA Validation | High | EXL/ Prudential | Could have an impact on the number of audits and timeliness of audits |  | 2021-08-27 | TBD
2
Closed Action Items
1 | Applications Access | Appplications access to be granted to internally seeded associates | High | Prudential | Associates will not be able to perform hands on work | Access request has already been raised with Prudential tech team 06/18 Only ERS access issue is pending for one associate | 2021-06-08 | 2021-06-11 | 2021-06-22
2 | Documentation | RSA Validation and Follow Up Letters SOPs to be updated | High | Prudential | Less clarity on the procedures and more chances of errors | The topics that need updation, have been shared by Ranjan | 2021-07-01 | 2021-07-23 | 2021-07-23
3 | Documentation | Additions to the RSA Validation and Follwup Letters SOP | High | Prudential | Procedures not available for ceratin processes | Additional questions have been shared by EXL team on 7/27, Prudential team will review and update | 2021-07-26 | 2021-08-06 | 2021-08-04
4 | Quality Audits | EXL team to check internally the plan for QCA identification, as the QR transition is also active in parallel | High | EXL | Might have an impact on the time taken for QCA training | The names of identified QCA i.e. Arjoo, Sheela and Gaurav have been shared with the EXL Transitions team managing the QR transition, they would be trained and certified by Chris Pirc's team to take on the QCA role | 2021-08-09 | 2021-08-10 | 2021-08-10

## Issues
Log # | Date Identified | Category | Description of Issue | Priority | Owner | Status | Impact | Resolution | Comments | Target Resolution Date | Actual Resolution Date
Open Issues
1
2
3
Closed Issues
1 | 2021-04-28 | Hiring | Back Ground Check for New Hires | High | EXL | Closed | The background checks and drug tests for new hires will be delayed due to the COVID-19 related lockdown. Only virtual verifications are feasible as of now, physical verifications will be completed later. | Exception approval sought from Prudential |  | 2021-04-30 | 2021-05-13
2

## BGC & Drug Test
Emp ID. | Participants / Trainees | BGC Status | Drug Test Status
162623 | Amit Kumar Rai | In Progress | Cleared
162629 | Harsh Vardhan Shahi | Cleared | Cleared
162624 | Jyoti . | In Progress | Cleared
162626 | Kusum . | In Progress | Cleared
162628 | Naveen Kumar | Cleared | Cleared
162630 | Neelam Kumari | In Progress | Cleared
162631 | Neetu Gautam | Cleared | Cleared
162633 | Shristi Maheshwari | Cleared | Cleared
162625 | Shweta Singh | Cleared | Cleared
162627 | Gaurav Mishra | Cleared | Cleared
162632 | Yashika Gupta | Cleared | Cleared
162738 | Sheela Bagh | Cleared | Cleared
142990 | Trilok Sharma | Cleared | Cleared
136945 | Versha . | Cleared | Cleared
163556 | Aarjoo Ahmed Siddiqui | Cleared | Cleared
163998 | Gaurav Bhandari | In Progress | Cleared
164199 | Pinki Kashyap | In Progress | Cleared